## Forecast
|  |  |  | Ledger Type | AA
|  |  |  | Year | 2019
|  |  |  | Format | LTD
|  |  |  | Period | 6
|  |  |  | Currency | ***
City of Overland Park Cash Flow Projection
|  |  |  | Project Description: | Metcalf: 159th to 167th Street |  |  | Completed By: | Tony Rome
|  |  |  | C.I.P. Project Number: | TH-1027 |  |  | Last Updated: | 2019-06-28
|  |  |  | Total Project Amount: | 17005000
|  |  |  | DATES: | Month | Year |  | Instructions:
|  |  |  | Start Date | 1 | 2013 |  | -Data is to be entered by Engineer in Orange and Green Cells
|  |  |  | Completion Date | 12 | 2020 |  | -Other cells are formulas and should be lock to prevent accidently overwriting.
|  |  |  | Current Date | 6 | 2019 |  | -Actuals can be found on "actuals" tab (at bottom of page)
LTD
[5 empty] | Project Budget | 6/2019 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | from Jun-21 to 12/2020 | Total Projected Cash Flow | Variance - Projected to Budget
CO | BU | ObjectAcct | SubAcct | EXPENSES:
* | TH1027 | [7790,9780,9880,9882] | * | Construction Costs | 12500000 | 5536039.57 | 1000000 | 1500000 | 1550000 | 1000000 | 1500000 |  |  |  | 100000 | [15 empty] | 12186039.57 | -313960.43
* | TH1027 |  | * | Estimated Change Orders | 625000 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | [19 empty] | 250000 | -375000
* | TH1027 | 9040 | * | Consultant Inspection | 70000 | 0 | [24 empty] | 0 | -70000
* | TH1027 | 9220 | 51 | Materials Testing | 50000 | 24106.24 | 5000 | 5000 | 5000 | 2000 | [20 empty] | 41106.24 | -8893.76
* | TH1027 | 9060 | * | Design | 1000000 | 1164653.41 | 1500 | 1500 | 1500 | 1500 | 1500 | [19 empty] | 1172153.41 | 172153.41
* | TH1027 | 9000 | * | Consultant EDC |  | 0 | [24 empty] | 0 | 0
* | TH1027 | 9750.9751 | * | ROW and Easement Acquisition | 500000 | 478565 | [24 empty] | 478565 | -21435
* | TH1027 | 9881 | * | Utility Relocations | 2000000 | 581004.91 | 200000 | 200000 | 200000 | 200000 | 200000 | [19 empty] | 1581004.91 | -418995.09
* | TH1027 | 9220 | 5 | Financing |  | 8415.87 | [24 empty] | 8415.87 | 8415.87
* | TH1027 | [7280,8800,9020,9070,9500,9530,9752] | * | Administrative Costs | 10000 | 98462.68 | [24 empty] | 98462.68 | 88462.68
* | TH1027 | [9710.9740,9883] | * | Land Acquisition |  | 146188 | [24 empty] | 146188 | 146188
* | TH1027 | [9690,9870,8420,8430] | * | Other | 250000 | 305130 | [24 empty] | 305130 | 55130
|  |  |  | Forecasted Expenditures: | 17005000 |  | 1256500 | 1756500 | 1806500 | 1253500 | 1751500 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16267065.68 | -737934.32
* | TH1027 | [7001.9999,/9901] | * | Actual Expenditures: |  | 8342565.68
REIMBURSEMENTS:
* | TH1027 | 6719 | 1CDBG | Community Development Block Grant | 0 | 0 | [24 empty] | 0 | 0
* | TH1027 | 6720 | 1CTY | Johnson County | 3392000 | 670114.73 | 150000 | 150000 | 150000 | 150000 | 775000 | 500000 | 200000 | 200000 | [16 empty] | 2945114.73 | -446885.27
* | TH1027 | 6720 | 1KDOT | KS Dept. of Transportation | 0 | 2531201.14 | 800000 | 800000 | 800000 | 890000 | 500000 | 200000 | [18 empty] | 6521201.14 | 6521201.14
* | TH1027 | 6720 | [1FED,1ISTEA,1TEA21,1OFED,1ARRA,1CORP,1EPA,10FED,ISTEA] | Federal Funding | 6640000 | 0 | [24 empty] | 0 | -6640000
* | TH1027 | 6720 | [1OCTY,10CTY] | Other Cities Funding | 0 | 0 | [24 empty] | 0 | 0
* | TH1027 | 6720 | [1WWD,1KCATA,1KDWP,1KST] | Other Intergovernmental Funding | 0 | 0 | [24 empty] | 0 | 0
* | TH1027 | 6901 | 180* | Private Funds/Escrows | 0 | 0 | [24 empty] | 0 | 0
[31 empty] | 0 | 0
|  |  |  | Forecasted Reimbursement: | 10032000 |  | 950000 | 950000 | 950000 | 1040000 | 1275000 | 700000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9466315.87 | -565684.13
|  |  |  | Actual Reimbursements: |  | 3201315.87
[5 empty] | Cash Flow In/(Out) | -5141249.81 | -306500 | -806500 | -856500 | -213500 | -476500 | 700000 | 200000 | 200000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6800749.81 | 172250.19
ERROR: Variance should be ZERO; Revise project budget or cash flow

## Actuals
|  |  |  | Ledger Type |  | AA | AA | AA | AA
|  |  |  | Year |  | 2019 | 2019 | 2019 | 2019
|  |  |  | Format |  | LTD | PER | PER | PER
|  |  |  | Period |  | 3 | 4 | 5 | 6
|  |  |  | Currency |  | *** | *** | *** | ***
TH-1027: Metcalf: 159th to 167th Street
Project Actuals in E1
[6 empty] | LTD | PER | PER | PER |  | Variance -
[5 empty] | Project Budget | 3/2019 | 4/2019 | 5/2019 | 6/2019 | Total LTD | Projected to LTD Actual
CO | BU | ObjectAcct | SubAcct | EXPENSES:
* | TH1027 | [9780,9880,9882] | * | Construction Costs | 12500000 | 3789727.76 | 159759.26 | 1586552.55 | 0 | 5536039.57 | -6963960.43
* | TH1027 |  | * | Estimated Change Orders | 625000 | 0 | 0 | 0 | 0 | 0 | -625000
* | TH1027 | 9040 | * | Consultant Inspection | 70000 | 0 | 0 | 0 | 0 | 0 | -70000
* | TH1027 | 9220 | 51 | Materials Testing | 50000 | 14713.74 | 1679 | 7713.5 | 0 | 24106.24 | -25893.76
* | TH1027 | 9060 | * | Design | 1000000 | 1159333.41 | 0 | 5320 | 0 | 1164653.41 | 164653.41
* | TH1027 | 9000 | * | Consultant EDC | 0 | 0 | 0 | 0 | 0 | 0 | 0
* | TH1027 | 9750.9751 | * | ROW and Easement Acquisition | 500000 | 478565 | 0 | 0 | 0 | 478565 | -21435
* | TH1027 | 9881 | * | Utility Relocations | 2000000 | 227147.44 | 0 | 353857.47 | 0 | 581004.91 | -1418995.09
* | TH1027 | 9220 | 5 | Financing | 0 | 8415.87 | 0 | 0 | 0 | 8415.87 | 8415.87
* | TH1027 | [7280,8800,9020,9070,9500,9530,9752] | * | Administrative Costs | 10000 | 98462.68 | 0 | 0 | 0 | 98462.68 | 88462.68
* | TH1027 | [9710.9740,9883] | * | Land Acquisition | 0 | 146188 | 0 | 0 | 0 | 146188 | 146188
* | TH1027 | [9690,9870,8420,8430] | * | Other | 250000 | 305130 | 0 | 0 | 0 | 305130 | 55130
|  |  |  | Forecasted Expenditures: | 17005000
* | TH1027 | [7001.9999,/9901] | * | Actual Expenditures: |  | 6227683.9 | 161438.26 | 1953443.52 | 0 | 8342565.68 | -8662434.32
REIMBURSEMENTS:
* | TH1027 | 6719 | 1cdbg | Community Development Block Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0
* | TH1027 | 6720 | 1cty | Johnson County | 3392000 | 0 | 0 | 0 | 0 | 0 | 3392000
* | TH1027 | 6720 | 1kdot | KS Dept. of Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0
* | TH1027 | 6720 | [1fed,1istea,1tea21,1ofed,1arra,1corp,1epa,10fed,ISTEA] | Federal Funding | 6640000 | 0 | 0 | 0 | 0 | 0 | 6640000
* | TH1027 | 6720 | [1octy,10cty] | Other Cities Funding | 0 | 0 | 0 | 0 | 0 | 0 | 0
* | TH1027 | 6720 | [1WWD,1KCATA,1KDWP,1KST] | Other Intergovernmental Funding | 0 | 0 | 0 | 0 | 0 | 0 | 0
* | TH1027 | 6901 | 180* | Private Funds/Escrows | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0
|  |  |  | Forecasted Reimbursement: | 10032000
|  |  |  | Actual Reimbursements: |  | 0 | 0 | 0 | 0 | 0 | 10032000
[5 empty] | Cash Flow In/(Out) | -6227683.9 | -161438.26 | -1953443.52 | 0 | -8342565.68 | 0