## Final Payment
Project: 159th Street - Metcalf to Nall
City Project No: TH-0513 |  | Original Contract Amt: $7,879,071.50
KDOT Project No: 46 N-0607-01
CARS Project No: 320001113 |  | Revised Contract Amt per CO 1: $7,880,714.59
Pay Estimate No.: Final Payment
Contractor: O'Donnell & Sons
15301 Broadmoor St
Overland Park, KS 66223
Item | Item Description | Unit | Quantity | Unit | Participating | Non-Participating | Total | Total | Total
No. |  |  |  | Price | Complete | Complete | Participating | Non-Participating | Complete
1 | Force Account (Set) * | Lump Sum | 1 | 250000 |  |  | 0 | 0 | 0
A | Tree Removal and Replacement SE Outlook | Lump Sum | 1 | 3454 |  | 0.013816 | 0 | 3454 | 3454
B | Temporary Fence Upgrade | Lump Sum | 1 | 8437 |  | 0.033748 |  | 8437 | 8437
C | Temporary Fence Upgrade Tract 26 | Lump Sum | 1 | 3354 |  | 0.013416 |  | 3354 | 3354
D | Round About Median Conduit | Lump Sum | 1 | 3388 |  | 0.013552 |  | 3388 | 3388
D | Round About Median Conduit | Lump Sum | 1 | 3388 |  | 0.013552 |  | 3388 | 3388
E | Curb Inlet | Lump Sum | 1 | 5500 |  | 0.022 |  | 5500 | 5500
F | D Curb East of Nall | Lump Sum | 1 | 3107.1 |  | 0.012428 |  | 3107.1 | 3107.1
G | NE Nall & 159th Signal Conflict | Lump Sum | 1 | 6065 |  | 0.02426 |  | 6065 | 6065
H | Signal Pole Rework SE of Nall | Lump Sum | 1 | 5192 |  | 0.020768 |  | 5192 | 5192
I | Grading East of Nall | Lump Sum | 1 | 1374.46 |  | 0.0054978 |  | 1374.46 | 1374.46
J | Modular Block Wall at Woodson | Lump Sum | 1 | 1375 |  | 0.0055 |  | 1375 | 1375
K | Tract #34 Plantings | Lump Sum | 1 | 385 |  | 0.00154 |  | 385 | 385
L | Concrete Pavement Markings | Lump Sum | 1 | 10521.5 |  | 0.042086 |  | 10521.5 | 10521.5
M | Tree Removal at 6399 159th Street | Lump Sum | 1 | 1232 |  | 0.004928 |  | 1232 | 1232
N | Letter N Tree Stump Grinding at 6029 W. 158th Street | Lump Sum | 1 | 313.5 |  | 0.001254 |  | 313.5 | 313.5
O | Letter O Concrete removal | Lump Sum | 1 | 3352.88 |  | 0.013412 |  | 3352.88 | 3352.88
P | RRFB Price Increase | Lump Sum | 1 | 1255.8 |  | 0.0050232 |  | 1255.8 | 1255.8
Q | Letter Q Concrete Removal | Lump Sum | 1 | 5572.71 |  | 0.022291 |  | 5572.71 | 5572.71
R | Letter R Ped wings | Lump Sum | 1 | 500 |  | 0.002 |  | 500 | 500
S | Letter S Sump Connect | Lump Sum | 1 | 914.25 |  | 0.003657 |  | 914.25 | 914.25
T | Letter T Willow Bend prep | Lump Sum | 1 | 18428.75 |  | 0.073715 |  | 18428.75 | 18428.75
U | Letter U Tract 131 Grading | Lump Sum | 1 | 281.75 |  | 0.001127 |  | 281.75 | 281.75
2 | Contractor Construction Staking | Lump Sum | 1 | 47500 | 1 |  | 47500 | 0 | 47500
3 | Maintenance Bond * | Lump Sum | 1 | 42500 |  | 1 | 0 | 42500 | 42500
4 | Clearing & Grubbing | Lump Sum | 1 | 80000 | 1 |  | 80000 | 0 | 80000
5 | Removal of Existing Structures | Lump Sum | 1 | 250000 | 1 |  | 250000 | 0 | 250000
6 | Unclassified Excavation | Cu. Yd. | 29330 | 22.5 | 29330 |  | 659925 | 0 | 659925
7 | Compaction of Earthwork (All Types) | Cu. Yd. | 9419 | 5 | 9419 |  | 47095 | 0 | 47095
8 | Excavation (Unsuitable) | Cu. Yd. | 2000 | 10 | 3118.22 |  | 31182.2 | 0 | 31182.2
9 | Topsoil | Cu. Yd. | 1500 | 7.5 | 0 |  | 0 | 0 | 0
10 | Asphaltic Concrete Surface Course | Ton | 4802 | 60 | 5036.71 |  | 302202.6 | 0 | 302202.6
11 | Asphaltic Concrete Intermediate Course | Ton | 18701 | 58 | 18452.51 |  | 1070245.58 | 0 | 1070245.58
12 | Aggregate Base Course (OP Special) (6") | Sq. Yd. | 44885 | 6.1 | 42747.5 |  | 260759.75 | 0 | 260759.75
13 | Fly Ash | Ton | 2943 | 40 | 2538.04 |  | 101521.6 | 0 | 101521.6
14 | Manipulation for Fly Ash Treated Subgrade (8") | Sq. Yd. | 49544 | 1.75 | 48405.5 |  | 84709.63 | 0 | 84709.625
15 | Milling (Total Width Cut) (2") | Sq. Yd. | 3247 | 4 | 3247 |  | 12988 | 0 | 12988
16 | Temporary Surfacing Material (Hot Mix Asphalt - Commercial Grade (Intermediate Course) (est) | Ton | 2000 | 80 | 1980.87 |  | 158469.6 | 0 | 158469.6
17 | Temporary Surfacing Material (AB-3 O.P. Modified) (est) | Ton | 5000 | 19.5 | 80.36 |  | 1567.02 | 0 | 1567.02
18 | Asphalt Patching (est.) | Ton | 250 | 100 | 0 |  | 0 | 0 | 0
19 | Curb & Gutter, Combined (Type A) | Lin. Feet | 355 | 14.65 | 201.53 |  | 2952.41 | 0 | 2952.4145
20 | Curb & Gutter, Combined (Type B) | Lin. Feet | 10597 | 16 | 11403.05 |  | 182448.8 | 0 | 182448.8
21 | Curb & Gutter, Combined (Type E) | Lin. Feet | 10577 | 13.65 | 10420.05 |  | 142233.68 | 0 | 142233.6825
22 | Curb & Gutter, Combined (Special) | Lin. Feet | 804 | 19.45 | 821 |  | 15968.45 | 0 | 15968.45
23 | Concrete Base Widening | Sq. Ft. | 920 | 5.1 | 1791.62 |  | 9137.26 | 0 | 9137.262
24 | Concrete Median Nose | Each | 6 | 1300 | 5 |  | 6500 | 0 | 6500
25 | Concrete Pavers | Sq. Ft. | 5327 | 14.2 |  |  | 0 | 0 | 0
26 | Concrete Truck Apron Pavers | Sq. Ft. | 4234 | 14.3 |  |  | 0 | 0 | 0
25A | ASTM C1272 Concrete Pavers | Sq. Ft. | 5327 | 14.27 | 3715.1 |  | 53014.48 | 0 | 53014.477
26A | ASTM C1272 Concrete Truck Apron Pavers | Sq. Ft. | 4234 | 14.6 | 4234.4 |  | 61822.24 |  | 61822.24
27 | Concrete Entrance Pavement - Residential (6") | Sq. Yd. | 1198 | 58.65 | 1353.27 |  | 79369.29 | 0 | 79369.2855
28 | Concrete Entrance Pavement - Commercial (6") | Sq. Yd. | 885 | 58.65 | 736.7 |  | 43207.46 | 0 | 43207.455
29 | Asphalt Driveway (Intermediate Course) (6") | Ton | 21 | 155 | 20.09 |  | 3113.95 | 0 | 3113.95
30 | Sidewalk Construction (4") | Sq. Ft. | 32966 | 4.05 | 23185.4 |  | 93900.87 | 0 | 93900.87
31 | Sidewalk Ramp w/ Detectable Warning Surface | Sq. Ft. | 2869 | 9.3 | 3025.26 |  | 28134.92 | 0 | 28134.918
32 | Detectable Warning Surface | Sq. Ft. | 612 | 40 | 701.45 |  | 28058 | 0 | 28058
33 | Sidewalk Ramp Curb | Lin. Feet | 156 | 31.7 | 9 |  | 285.3 | 0 | 285.3
34 | Asphalt Sidewalk (Intermediate Course) (4") | Ton | 1092 | 66.25 | 1300.83 |  | 86179.99 | 0 | 86179.9875
35 | Aggregate Base (AB-3 O.P. Modified - 4" under asphalt trail) | Sq Yd. | 5054 | 4.25 | 5577.29 |  | 23703.48 | 0 | 23703.4825
36 | Modular Block Retaining Wall | Sq. Ft. | 576 | 40 | 576 |  | 23040 | 0 | 23040
37 | KCMMB 4k Concrete - Integral Sidewalk Retaining Wall | Cu. Yd. | 207 | 870 | 233.01 |  | 202718.7 | 0 | 202718.7
38 | KCMMB 5k Concrete (cast in place Retaining Wall - form lined face) | Cu. Yd. | 241 | 780 | 228.8 |  | 178464 | 0 | 178464
39 | Handrail (42-inch Metal) | Lin. Feet | 297 | 140 | 295.5 |  | 41370 | 0 | 41370
40 | 15" RCP Class III Storm Sewer | Lin. Feet | 2951 | 56 | 2951 |  | 165256 | 0 | 165256
41 | 18" RCP Class III Storm Sewer | Lin. Feet | 1372 | 62 | 1372 |  | 85064 | 0 | 85064
42 | 24" RCP Class III Storm Sewer | Lin. Feet | 1148 | 72 | 1148 |  | 82656 | 0 | 82656
43 | 30" RCP Class III Storm Sewer | Lin. Feet | 1700 | 86 | 1700 |  | 146200 | 0 | 146200
44 | 36" RCP Class III Storm Sewer | Lin. Feet | 286 | 134 | 286 |  | 38324 | 0 | 38324
45 | 42" RCP Class III Storm Sewer | Lin. Feet | 482 | 206 | 482 |  | 99292 | 0 | 99292
46 | 48" RCP Class III Storm Sewer | Lin. Feet | 282 | 211 | 282 |  | 59502 | 0 | 59502
47 | 54" RCP Class III Storm Sewer | Lin. Feet | 114 | 232 | 114 |  | 26448 | 0 | 26448
48 | 15" End Section (RC Class III) | Each | 1 | 1365 | 1 |  | 1365 | 0 | 1365
49 | 18" End Section (RC Class III) | Each | 1 | 1445 | 1 |  | 1445 | 0 | 1445
50 | 30" End Section (RC Class III) | Each | 1 | 1675 | 1 |  | 1675 | 0 | 1675
51 | 48" End Section (RC Class III) | Each | 1 | 2190 | 1 |  | 2190 | 0 | 2190
52 | 54" End Section (RC Class III) | Each | 1 | 2370 | 1 |  | 2370 | 0 | 2370
53 | 6' x 4' Curb Inlet | Each | 32 | 5155 | 32 |  | 164960 | 0 | 164960
54 | 6' x 6' Curb Inlet | Each | 1 | 5930 | 1 |  | 5930 | 0 | 5930
55 | 8' x 4' Curb Inlet | Each | 3 | 6700 | 3 |  | 20100 | 0 | 20100
56 | 8' x 6' Curb Inlet | Each | 2 | 7730 | 2 |  | 15460 | 0 | 15460
57 | 10' x 4' Curb Inlet | Each | 3 | 7215 | 3 |  | 21645 | 0 | 21645
58 | 4' x 4' Median Inlet | Each | 5 | 4950 | 5 |  | 24750 | 0 | 24750
59 | 4' x 4' Junction Box | Each | 7 | 4750 | 7 |  | 33250 | 0 | 33250
60 | 5' x 5' Junction Box | Each | 2 | 5670 | 2 |  | 11340 | 0 | 11340
61 | 6' x 4' Junction Box | Each | 1 | 5360 | 1 |  | 5360 | 0 | 5360
62 | 6' x 6' Junction Box | Each | 3 | 6185 | 3 |  | 18555 | 0 | 18555
63 | 7' x 5' Junction Box | Each | 1 | 6080 | 1 |  | 6080 | 0 | 6080
64 | 3' x 3' Area Inlet | Each | 5 | 4950 | 5 |  | 24750 | 0 | 24750
65 | 4' x 4' Area Inlet | Each | 1 | 5155 | 1 |  | 5155 | 0 | 5155
66 | 6' x 6' Area Inlet | Each | 1 | 6390 | 1 |  | 6390 | 0 | 6390
67 | Grate Inlet (Special) | Each | 2 | 5670 | 2 |  | 11340 | 0 | 11340
68 | SQU Structure (Sta. 206+06) | Each | 1 | 46400 | 1 |  | 46400 | 0 | 46400
69 | SQU Structure (Sta. 208+35) | Each | 1 | 43300 | 1 |  | 43300 | 0 | 43300
70 | SQU Structure (Sta. 238+01) | Each | 1 | 33000 | 1 |  | 33000 | 0 | 33000
71 | SQU Structure (Sta. 242+72) | Each | 1 | 43300 | 1 |  | 43300 | 0 | 43300
72 | Concrete Collar | Each | 2 | 2580 | 1 |  | 2580 | 0 | 2580
73 | Riprap (Light Series 24") | Sq. Yd. | 223 | 72 | 194.32 |  | 13991.04 | 0 | 13991.04
74 | Pipe Underdrain (6") (All Types) | Lin. Feet | 11648 | 13.5 | 14974.32 |  | 202153.32 | 0 | 202153.32
75 | Private Drainage Connection * | Each | 6 | 1340 |  | 6.5 | 0 | 8710 | 8710
76 | 4' Dia. Sanitary Sewer Manhole * | Each | 2 | 4950 |  | 2 | 0 | 9900 | 9900
77 | 5' Dia. Sanitary Sewer Manole * | Each | 1 | 5360 |  | 1 | 0 | 5360 | 5360
78 | Concrete Sanitary Sewer Encasement * | Lin. Feet | 179 | 85 |  | 179 | 0 | 15215 | 15215
79 | 6" HDPE SDR-17 w/ Tracer Wire Sanitary Sewer * | Lin. Feet | 342 | 57 |  | 559.7 | 0 | 31902.9 | 31902.9
80 | 8" PVC SDR-35 Sanitary Sewer * | Lin. Feet | 56 | 72 |  | 55.5 | 0 | 3996 | 3996
81 | 8" DIP Protecto 401 Sanitary Sewer * | Lin. Feet | 162 | 125 |  | 167 | 0 | 20875 | 20875
82 | Cleanout Sanitary Sewer * | Each | 5 | 670 |  | 6 | 0 | 4020 | 4020
83 | Orange Construction Fence (Temporary) * | Lin. Feet | 1000 | 3 |  | 850 | 0 | 2550 | 2550
84 | 72" Chain Link Fence (Temporary) * | Lin. Feet | 1994 | 10 |  | 3003.28 | 0 | 30032.8 | 30032.8
85 | 48" Chain Link Fence (Permanent) * | Lin. Feet | 205 | 30 |  | 505.5 | 0 | 15165 | 15165
86 | 48" Wood Privacy Fence (Permanent) * | Lin. Feet | 150 | 20 |  | 289.4 | 0 | 5788 | 5788
87 | 72" Wood Privacy Fence (Permanent) * | Lin. Feet | 1291 | 28 |  | 1811.1 | 0 | 50710.8 | 50710.8
88 | 72" Special Wood Privacy Fence (Permanent) * | Lin. Feet | 128 | 37 |  | 150.8 | 0 | 5579.6 | 5579.6
89 | Street Lighting Installation | Lump Sum | 1 | 233350 | 1 |  | 233350 | 0 | 233350
90 | Fiber-Optic Communication System | Lump Sum | 1 | 53600 | 1 |  | 53600 | 0 | 53600
91 | Traffic Signal Installation (159th and Nall) | Lump Sum | 1 | 230900 | 1 |  | 230900 | 0 | 230900
92 | Traffic Signal Modification (159th and Metcalf) | Lump Sum | 1 | 1910 | 1 |  | 1910 | 0 | 1910
93 | Permanent Traffic Control Signs (MEP) | Sq. Ft. | 659 | 36 | 668 |  | 24048 | 0 | 24048
94 | 1-3/4" x 1-3/4" Sign Post | Lin. Feet | 854 | 8 | 866.32 |  | 6930.56 | 0 | 6930.56
95 | 2" x 2" Sign Post Anchors | Lin. Feet | 275 | 9 | 275 |  | 2475 | 0 | 2475
96 | 2-1/4" x 2-1/4" Anchor Sleeves | Lin. Feet | 120 | 10 | 120 |  | 1200 | 0 | 1200
97 | Rectangular Rapid Flashing Beacon Installation | Each | 12 | 6650 | 16 |  | 106400 | 0 | 106400
98 | Rectangular Rapid Flashing Beacon Pedestal Pole Foundation | Each | 10 | 595 | 12 |  | 7140 | 0 | 7140
99 | Traffic Control | Lump Sum | 1 | 149000 | 1 |  | 149000 | 0 | 149000
100 | 4" White Thermoplastic | Lin. Feet | 15622 | 0.6 | 15622 |  | 9373.2 | 0 | 9373.2
101 | 4" Yellow Themoplastic | Lin. Feet | 4641 | 0.65 | 4641 |  | 3016.65 | 0 | 3016.65
102 | 8" White Thermoplastic | Lin. Feet | 1406 | 1.1 | 1406 |  | 1546.6 | 0 | 1546.6
103 | 6" White Pre-Formed Thermoplastic | Lin. Feet | 1358 | 3.1 | 1358 |  | 4209.8 | 0 | 4209.8
104 | 12" White Pre-Formed Thermoplastic | Lin. Feet | 333 | 6.2 | 333 |  | 2064.6 | 0 | 2064.6
105 | 12" Yellow Pre-Formed Thermoplastic | Lin. Feet | 300 | 6.2 | 300 |  | 1860 | 0 | 1860
106 | 24" White Pre-Formed Thermoplastic | Lin. Feet | 196 | 14.45 | 196 |  | 2832.2 | 0 | 2832.2
107 | White Turn Arrows Pre-Formed Thermoplastic | Each | 26 | 170 | 26 |  | 4420 | 0 | 4420
108 | White Thru Arrows Pre-Formed Thermoplastic | Each | 4 | 150 | 4 |  | 600 | 0 | 600
109 | White Thru/Turn Arrows Pre-Formed Thermoplastic | Each | 8 | 295 | 8 |  | 2360 | 0 | 2360
110 | White Merge Arrows Pre-Formed Thermoplastic | Each | 2 | 480 | 2 |  | 960 | 0 | 960
111 | 24"x36" White Yield Lines Thermoplastic | Each | 37 | 16.5 | 37 |  | 610.5 | 0 | 610.5
112 | White Bike Lane Rider Thermoplastic | Each | 15 | 270 | 15 |  | 4050 | 0 | 4050
113 | White Bike Lane Arrows Thermoplastic | Each | 15 | 190 | 15 |  | 2850 | 0 | 2850
114 | Temporary Pavement Marking | Lump Sum | 1 | 39175 | 1 |  | 39175 | 0 | 39175
115 | Willow Bend at the Village Irrigation Relocation * | Lump Sum | 1 | 18560 |  | 1 | 0 | 18560 | 18560
116 | Sylvan Lake Irrigation Relocation * | Lump Sum | 1 | 3100 |  | 1 | 0 | 3100 | 3100
117 | Hampton Place Irrigation Relocation * | Lump Sum | 1 | 12375 |  | 1 | 0 | 12375 | 12375
118 | Wilderness Irrigation Relocation * | Lump Sum | 1 | 12375 |  | 1 | 0 | 12375 | 12375
119 | Tract 30 Irrigation Relocation * | Lump Sum | 1 | 3100 |  | 1 | 0 | 3100 | 3100
120 | Service Water Line Relocation (Est) * | Lin. Feet | 250 | 51.55 |  | 0 | 0 | 0 | 0
121 | Water Pollution Control Manager | Each | 80 | 200 | 65 |  | 13000 | 0 | 13000
122 | SWPPP Inspection (Est) | Each | 100 | 200 | 61 |  | 12200 | 0 | 12200
123 | Erosion Control Blanket Class 1 (Type A) | Sq. Yd. | 1241 | 2 | 710 |  | 1420 | 0 | 1420
124 | Biodegradable Log (9") | Lin. Feet | 12800 | 3.5 | 3292 |  | 11522 | 0 | 11522
125 | Construction Entrance | Sq. Yd. | 150 | 10 | 223.2 |  | 2232 | 0 | 2232
126 | Hydraulic Erosion Control (Type 1)(Est) | Ton | 6 | 1305 | 0 |  | 0 | 0 | 0
127 | Hydraulic Erosion Control (Type 3)(Est) | Ton | 13 | 1450 | 5.31 |  | 7699.5 | 0 | 7699.5
128 | Hydraulic Erosion Control (Type 5)(Est) | Ton | 40 | 2225 | 0 |  | 0 | 0 | 0
129 | Temporary Ditch Checks (Rock) | Each | 4 | 500 | 36 |  | 18000 | 0 | 18000
130 | Temporary Filter Berm (est.) | Lin. Feet | 200 | 21 | 0 |  | 0 | 0 | 0
131 | Filter Sock (6")(est.) | Lin. Feet | 500 | 5.25 | 0 |  | 0 | 0 | 0
132 | Temporary Inlet Sediment Barrier (Existing Curb Inlet) | Each | 17 | 3.4 | 24 |  | 81.6 | 0 | 81.6
133 | Temporary Inlet Sediment Barrier (Curb Inlet) | Each | 45 | 145 | 45 |  | 6525 | 0 | 6525
134 | Temporary Inlet Sediment Barrier (Existing Area Inlet) | Each | 1 | 175 | 1 |  | 175 | 0 | 175
135 | Temporary Inlet Sediment Barrier (Area Inlet) | Each | 7 | 190 | 5 |  | 950 | 0 | 950
136 | Temporary Inlet Sediment Barrier (Existing Junction Box) | Each | 1 | 190 | 1 |  | 190 | 0 | 190
137 | Temporary Inlet Sediment Barrier (Junction Box) | Each | 15 | 190 | 2 |  | 380 | 0 | 380
138 | Temporary Inlet Sediment Barrier (SQ Unit) | Each | 4 | 160 | 0 |  | 0 | 0 | 0
139 | Temporary Inlet Sediment Barrier (Sanitary) | Each | 3 | 160 | 0 |  | 0 | 0 | 0
140 | Temporary Sediment Trap | Each | 2 | 160 | 0 |  | 0 | 0 | 0
141 | Silt Fence | Lin. Feet | 6430 | 2 | 5212.8 |  | 10425.6 | 0 | 10425.6
142 | Storm Sewer 18" CMP | Lin. Feet | 42 | 50 | 0 |  | 0 | 0 | 0
143 | Storm Sewer 36" x 24" CMPA | Lin. Feet | 76 | 70 | 0 |  | 0 | 0 | 0
144 | Temporary Seed | Acre | 30 | 990 | 3.05 |  | 3019.5 | 0 | 3019.5
145 | Fescue Sod | Sq. Yd. | 8079 | 4.7 | 14036 |  | 65969.2 | 0 | 65969.2
146 | Bluegrass Sod | Sq. Yd. | 37615 | 4.4 | 33220 |  | 146168 | 0 | 146168
147 | Land Corner Monument Box | Each | 2 | 1500 | 2 |  | 3000 | 0 | 3000
148 | Change Order #1 See Bid Items 25A and 26A Dated June 22, 2016 |  |  |  | 0 |  | 0 | 0 | 0
149 | Change Order #2 (No Cost) Dated June 28, 2017 |  |  |  | 0 |  | 0 | 0 | 0
150 |  |  |  |  | 0 |  | 0 | 0 | 0
[5 empty] | Total |  | 7085205.13 | 389207.8 | 7474412.9195
Work Type Summary
[6 empty] | Common Items | 377500 | 44045.5 | 421545.5
[6 empty] | Roadway | 4189600.65 | 332649.5 | 4522250.154
[6 empty] | Surfacing | 2118154.48 | 0 | 2118154.4655
[6 empty] | Traffic Signals | 399950 | 12512.8 | 412462.8
[6 empty] | Totals: | 7085205.13 | 389207.8 | 7474412.9195