PROGRESS MEETING AGENDA

**QUIVIRA ROAD WIDENING (99TH STREET TO 105TH STREET)**

OVERLAND PARK NO. TH-0948 – JOHNSON COUNTY NO. 320000908 – KDOT NO. 46 N-0474-01

# **Dennis Garrett Maintenance Facility Conference Room (11300 W. 91st Street)**

# **February 10, 2012 – 10:00 a.m.**

1. Contract Time Requirements
* Complete all Phase 1, 2A, 2B, 3, and 4 work and open all lanes to traffic by August 31, 2012.
* Complete all Phase 5 work and all Phase 1, 2A, 2B, 3, 4 and 5 punch list items by October 12, 2012.
* Liquidated Damages: $2,500/day, including weekends and holidays.
1. Work Items Completed Since Last Meeting
2. Work Items Scheduled Prior to Next Meeting
3. Work Items From Contractor Construction Schedule Approved on February 6, 2012
* Last Week - Phase 1 Traffic Signals (subsurface). Phase 1 (SB) Install storm sewer.
* This Week – Phase 1 Traffic Signals (subsurface). Install storm sewer, clearing & grubbing, rough grading and removals. Fly Ash, irrigation, monuments.
* Next Week – Phase 1 Traffic Signals (subsurface). Clearing, grubbing, rough grading & removals. Fly Ash, Edge drain.
1. Utility Relocations
* KCPL poles - Last poles (2) to be removed after signals switched over – 99th & 103rd.
* WaterONE - Remaining priorities.
* West 103rd Street
* Cleanup West 101st Terrace
* NE corner East 103rd Street
* West 105th Street
* East 105th Street
* Sta 104+40
* Cleanup
* AT&T conflict?
1. Contractor Submittals
* Three copies of all submittals
* Asphalt – need resubmittal as discussed – Tony has contacted O’Donnell.

7. Erosion and Sediment Control

* Inspections every 7 days and after 0.5 inch rain event.

8. Outstanding Issues/Concerns

* Miles Excavating, Inc.
* HNTB Corporation

* The City of Overland Park, KS – Inspectors
* The City of Overland Park, KS – Project Manager
* Updated schedule? – need to reflect phase change and possible delay from traffic signal order.
* Force Account Items – Approved 1,2,3,6. Need 4 and 5.
* Monument reconstruction
* Forms to KDOT prior to payment