## Sheet1
Quivira Road Widening (99th Street to 105th Street KDOT PROJECT NO. 46 N-0474-01 (FEDERAL PROJECT NO. STP-N047 (401))
City Project No. TH-0948
|  | SUBMITTAL CHECKLIST |  |  |  | 2011-12-05
PQL = | KDOT Pre-Qualified Materials List
AML = | City of Overland Park Pre-Qualified Materials List
CO = | Consultant
CI = | Construction Inspector
PM = | Project Manager
TS = | Traffic Services
KDOT Type "" Certification (Section 2600 of Standard Specifications)
|  |  | Primary | Date | Date | Date
Item | Description | Submittal | Reviewer | Submitted | Reviewed | Approved
Subcontractor List
| Original Subcontractor List | List | PM
Construction Schedule
| Original Construction Schedule | Schedule | PM
| Working Hours | Letter | PM
Construction Video / Photos
| Preconstruction | Video / Photos on CD | CI
| Post Construction | Video / Photos on CD | CI
Aggregates
| Aggregate (3/4") | KDOT Type B Certification | CI
| Aggregate OP Special | KDOT Type B Certification | CI
| Aggregate (UD-1) | KDOT Type B Certification | CI
| Aggregate (PB-2) | KDOT Type B Certification | CI
| Aggregate (AB-3) | KDOT Type B Certification | CI
| Geotextile Fabric Class 1 | AML or KDOT Type D Certification | CI
Asphalt
| Asphaltic Concrete (Surface Course) | Mix Design or last mix produced | CI
| Asphaltic Concrete (Intermediate Course) | Mix Design or last mix produced | CI
| Temporary Surfacing Material Commercial Grade Asphalt | Mix Design or last mix produced | CI
Sidewalk, Curb, Driveways, Pipe Collars, Inverts, etc.
| 4K KCMMB Concrete | Mix Design Number from KCMMB | CI
| 5K KCMMB Concrete | Mix Design Number from KCMMB | CI
| Flowable Fill | Mix Design and Comp. Strength Test | CI
| Expansion Material | AML or KDOT Type D Certification | CI
| 10" #4 Dowel Bars | KDOT Type A Certification | CI
| Reinforcing Steel Grade 60 | KDOT Type A Certification | CI
| Liquid Membrane-Forming Compounds (Curing Compound) | AML or KDOT Type C Certification | CI
Sidewalk Ramps
| Reinforcing Steel (Epoxy) Grade 60 | KDOT Type A Certification | CI
| 18" #4 Tie/Dowel Bars | KDOT Type A Certification | CI
| Type "M" Mortar | KDOT Type D Certification | CI
| Detectable Warning Pavers | AML or KDOT Type A Certification | CI
Paver Brick
| Concrete Paver Stones | AML or KDOT Type A Certification | CI
Retaining Wall
| Concrete KCMMB 4K | Mix Design Number from KCMMB | CI
| Concrete KCMMB 5K | Mix Design Number from KCMMB | CI
| Reinforcing Steel Grade 60 | KDOT Type A Certification | CI
| 3/4" Clean Rock | KDOT Type B Certification | CI
| Stone Masonry Form Liner | S-39.2 Overland Park Specification | CI
| Handrail Steel | KDOT Type A Certification | CI
| Handrail | Shop Drawings | CO
Storm Sewer
| Precast Structures | Shop Drawings and KCMMB Mix Design | CO
| Concrete Mix Design | KCMMB Mix Design No. | CI
| Flowable Fill | Mix Design and Comp. Strength Test | CI
| Buy American Cerification | KDOT Type C Certification | CI
| Manhole Steps | AML or KDOT Type D Certification | CI
| Post Construction Video | Video/Visual | CI
| Heavy Duty Ring and Lid | AML or KDOT Type A Certification | CI
| Medium Duty Ring and Lid | AML or KDOT Type A Certification | CI
| Reinforced Concrete Pipe | AML or KDOT Type D Certification | CI
| Inlet Steel Frame Supplier | AML or KDOT Type A Certification | CI
Edge Drain
| Edge Drain Type H | AML or KDOT Type C Certification | CI
| Edge Drain Type K | AML or KDOT Type C Certification | CI
| Geotextile Fabric Class 1 | AML or KDOT Type D Certification | CI
Fly Ash and Provider
| Fly Ash | KDOT Type B Certification | CI
Restoration
| Fescue Sod / Fertilizer | KDOT Type A Certification/Visual Inspection | CI
| Blue Grass Sod / Fertilizer | KDOT Type A Certification/Visual Inspection | CI
Fence (Temporary Chain Link)
| Posts | KDOT Type A Certification | CI
| Chain Link | KDOT Type A Certification | CI
Erosion Control
| Sediment Retention Wattle (9" Diameter) | AML or KDOT Type D Certification | CI
| Curb Inlet Protection | AML or KDOT Type D Certification | CI
| Area Inlet Protection | AML or KDOT Type D Certification | CI
| Rock Barrier (6") | KDOT Type B Certification | CI
| Silt Fence | AML or KDOT Type D Certification | CI
| Temporary Seed | KDOT Type C Certification | CI
| Hydraulic Mulching | AML or KDOT Type D Certification | CI
Sprinkler System
| Lawn Sprinkler System | Catalog Cuts | CO
Land Corner Monument Box
| Monument Box | KDOT Type D Certification | CI
Street Lighting
Junction Boxes &Service Boxes
| Type I Junction Box | Approved Materials Submittal Form | TS
| Type II Junction Box | Approved Materials Submittal Form | TS
Luminaires
| Cobra-head Luminaire (250W) | Approved Materials Submittal Form | TS
Lamps
| High Pressure Sodium (HPS) (250W) | Approved Materials Submittal Form | TS
Concrete Controller Foundation
| KCMMB4K Concrete Mix Design | Certification | TS | (approved under Traffic Signal)
Poles and Arms
| 40' Aluminum Pole with 12' Twin Bracket Arms | Approved Materials Submittal Form | TS
| 40' Aluminum Pole with 12' and 8' Bracket Arms | Approved Materials Submittal Form | TS
Connector Kits & Fuses
| Un-fused Disconnect | Approved Materials Submittal Form | TS
| Fused Disconnect | Approved Materials Submittal Form | TS
| Fuse (8 Amp) | Approved Materials Submittal Form | TS
| Multiple Tap Connector | Approved Materials Submittal Form | TS
| Splice Kit | Approved Materials Submittal Form | TS
Photocell
| Photocell | Approved Materials Submittal Form | TS
Screw-in Foundations
| Type F2 Foundation Anchor | Approved Materials Submittal Form | TS
Grounding Equipment
| Ground Rod (1/2" x 10') | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| Ground Rod Clamp (1/2") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| Ground Wire (Bare Copper # 6 AWG) | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
Cable
| Distribution Cable (USE # 4 AWG) | Approved Materials Submittal Form | TS
| Pole Cable (THHN/THWN # 10 AWG) | Approved Materials Submittal Form | TS
Conduit and Fittings
| PVC Conduit (2") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| PVC Coupling (2") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| PVC Elbows (2") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| HDPE Street Lighting Conduit (2") | Approved Materials Submittal Form | TS
| HDPE Couplings (2") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
Break-away Pole Device
| Break-away Couplings / Frangible Base | Approved Materials Submittal Form | TS
Aluminum Control Centers
| Aluminum Control Center (Pad Mounted, 4-circuit) | Approved Materials Submittal Form | TS
| Aluminum Control Center (Pad Mounted, 1-circuit) | Approved Materials Submittal Form | TS
Traffic Signals
Signal Heads
| Vehicular Signal Head (3-section) | Approved Materials Submittal Form | TS
| Vehicular Signal Head (4-section) | Approved Materials Submittal Form | TS
| One-Section Pedestrian Signal Head | Approved Materials Submittal Form | TS
| LED Lens (Red) | Approved Materials Submittal Form | TS
| LED Lens (Yellow) | Approved Materials Submittal Form | TS
| LED Lens (Green) | Approved Materials Submittal Form | TS
| LED Lens (Orange Hand/White Man Countdown) | Approved Materials Submittal Form | TS
| LED Single Arrow Kit (Yellow) | Approved Materials Submittal Form | TS
| LED Single Arrow Kit (Green) | Approved Materials Submittal Form | TS
| LED Dual Indication Lens (Green/Yellow Arrow) | Approved Materials Submittal Form | TS
Signal Head Brackets
| Mastarm Signal Head Bracket (Astro Brac) | Approved Materials Submittal Form | TS
| Pole Side-Mount Signal Head Bracket | Approved Materials Submittal Form | TS
| Pedestrian Head Bracket (clamshell mount) | Approved Materials Submittal Form | TS
| Mini Bracket (Pre-empt detector) | Approved Materials Submittal Form | TS
Backplates
| Vehicular Signal Backplate (3-section) | Approved Materials Submittal Form | TS
| Vehicular Signal Backplate (4-section) | Approved Materials Submittal Form | TS
Signal Poles
| Aluminum Pedestrian Pole (9') | Approved Materials Submittal Form | TS
| Aluminum Pedestrian Pole (13') | Approved Materials Submittal Form | TS
| Cast Aluminum Pedestrian Pole Base | Approved Materials Submittal Form | TS
| Signal Poles, Mast Arms, and Luminaire Arms (99th) | Shop Drawings | TS
| Signal Poles, Mast Arms, and Luminaire Arms (103rd) | Shop Drawings | TS
Junction Boxes & Service Boxes
| Type I Service Box | Approved Materials Submittal Form | TS
| Type II Service Box | Approved Materials Submittal Form | TS
Grounding Equipment
| Ground Rod (1/2" x 8') Service Boxes | Approved Materials Submittal Form | TS
| Ground Rod (1/2" x 10') Foundations | Approved Materials Submittal Form | TS
| Ground Rod Clamp (1/2") | Approved Materials Submittal Form | TS
| Ground Wire (Bare Copper # 6 AWG) | Approved Materials Submittal Form | TS
Cable
| Multi-conductor Signal Cable (7c # 14 AWG) | Approved Materials Submittal Form | TS
| Multi-conductor Signal Cable (2c # 14 AWG) | Approved Materials Submittal Form | TS
| CNG Power Cable | Approved Materials Submittal Form | TS
| CNG Monitoring Cable | Approved Materials Submittal Form | TS
| Video Detection Cable | Approved Materials Submittal Form | TS
| Pre-empt Detector Cable | Approved Materials Submittal Form | TS
| Radar Detector Cable | Approved Materials Submittal Form | TS
| CCTV Cat 5e Cable | Approved Materials Submittal Form | TS
| RWIS Data Cable | Approved Materials Submittal Form | TS
| RWIS Power Cable | Approved Materials Submittal Form | TS
| Stranded Copper Ground Cable (1c#10 AWG) | Approved Materials Submittal Form | TS
| Blankout Sign Cable (3c#14 AWG) | Approved Materials Submittal Form | TS
CCTV Camera
| CCTV Camera | Approved Materials Submittal Form | TS
| CCTV PoE Injector Module | Approved Materials Submittal Form | TS
| CCTV RJ-45 Plug-In Data Protector | Approved Materials Submittal Form | TS
Detectors
| Pre-empt Detector | Approved Materials Submittal Form | TS
| Radar Detector Assembly w/ Cable Harness | Approved Materials Submittal Form | TS
| Pedestrian Pushbutton | Approved Materials Submittal Form | TS
| RWIS Road Surface Condition Sensor w/ Cable Harness | Approved Materials Submittal Form | TS
| Video Detection System w/ Cameras | Approved Materials Submittal Form | TS
Conduit and Fittings
| PVC Conduit (2") | Approved Materials Submittal Form | TS
| PVC Coupling (2") | Approved Materials Submittal Form | TS
| PVC Elbow (2") | Approved Materials Submittal Form | TS
| PVC Elbow (3") | Approved Materials Submittal Form | TS
| PVC Elbow (4") | Approved Materials Submittal Form | TS
| HDPE Conduit (red w/ white stripe) (2") | Approved Materials Submittal Form | TS
| HDPE Conduit (red w/ white stripe) (3") | Approved Materials Submittal Form | TS
| HDPE Conduit (red w/ white stripe) (4") | Approved Materials Submittal Form | TS
| HDPE Coupling (2") | Approved Materials Submittal Form | TS
| HDPE Coupling (3") | Approved Materials Submittal Form | TS
| HDPE Coupling (4") | Approved Materials Submittal Form | TS
Backup Power Equipment
| CNG Generator & Cabinet | Approved Materials Submittal Form | TS
| CNG Generator Pad (if pre-cast polymer) | Approved Materials Submittal Form | TS
| UPS Battery Backup System | Approved Materials Submittal Form | TS
Controller & Equipment
| 2070 Signal Controller | Approved Materials Submittal Form | TS
| Conflict Monitor with Serial Port | Approved Materials Submittal Form | TS
| Flasher Unit | Approved Materials Submittal Form | TS
| Load Switch | Approved Materials Submittal Form | TS
| Flash Transfer Relay | Approved Materials Submittal Form | TS
| Surge Protector (power distribution) | Approved Materials Submittal Form | TS
| Surge Protector (video) | Approved Materials Submittal Form | TS
| Two-Channel DC Isolator | Approved Materials Submittal Form | TS
| Pre-emption Discriminator Module (4 channel) | Approved Materials Submittal Form | TS
| RWIS Sensor Control Unit | Approved Materials Submittal Form | TS
| Mini RWIS System RPU | Approved Materials Submittal Form | TS
| Power Distribution Unit (Rack Mounted) | Approved Materials Submittal Form | TS
| Adv. Radar Detector System | Approved Materials Submittal Form | TS
Miscellaneous Brackets
| Detector Camera Mounting Bracket (Lum Arm) | Approved Materials Submittal Form | TS
| Detector Camera Mounting Bracket (Side Pole) | Approved Materials Submittal Form | TS
| Radar Detector Mounting Bracket (Mast Arm) | Approved Materials Submittal Form | TS
| Combined Radar Detector and RWIS Road Sensor Bracket | Approved Materials Submittal Form | TS
| Sign Mounting Bracket (Mast Arm) | Approved Materials Submittal Form | TS
| Sign Mounting Bracket (Round Pole) | Approved Materials Submittal Form | TS
| CCTV Camera Mounting Bracket | Approved Materials Submittal Form | TS
Signs on Signal Poles
| Standard Signs (D9-2L, R3-4, R10-3E, R10-10, R10-12) | Catalog Cuts | TS
| Overhead Street Name Signs | Shop Drawings | TS
| LED Blankout Sign (R10-11) | Approved Materials Submittal Form | TS
| Sign Banding | Approved Materials Submittal Form | TS
| Banding Buckles | Approved Materials Submittal Form | TS
Controller Cabinet
| 333 Double Wide Pad-Mounted Cabinet | Approved Materials Submittal Form | TS
Aluminum Service Enclosure
| Secondary Aluminum Service Enclosure w/ 30 amp Main | Approved Materials Submittal Form | TS
Concrete Mix Design
| Signal Controller Foundation | Certification | TS
| Signal Pole Foundations | Certification | TS
Fiber Optic
Fiber Optic Locating Equipment
| 1c#10 AWG Tracer Cable | Approved Materials Submittal Form | TS
| Ground Rod (1/2" x 8') | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| Ground Rod Clamp (1/2") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
Service Boxes
| Type I Fiber Optic Service Box | Approved Materials Submittal Form | TS
| Type II Fiber Optic Service Box | Approved Materials Submittal Form | TS
Conduit and Fittings
| HDPE Fiber Conduit (3") | Approved Materials Submittal Form | TS
| HDPE Coupling (3") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
| PVC Elbow (3") | Approved Materials Submittal Form | TS | (approved under Traffic Signal)
Cable
| Fiber Optic Patch Cable | Approved Materials Submittal Form | TS
| 6-CT ITS Termination Drop Cable | Approved Materials Submittal Form | TS
Fiber Optic Termination Equipment
| Ethernet Switch | Approved Materials Submittal Form | TS
Pavement Marking
Thermoplastic
| Yellow Thermoplastic Pavement Markings | Approved Materials Submittal Form | TS
| White Thermoplastic Pavement Markings | Approved Materials Submittal Form | TS
Preformed Thermoplastic Tape
| 12" White | Approved Materials Submittal Form | TS
| 24" White | Approved Materials Submittal Form | TS
| White "ONLY" Text | Approved Materials Submittal Form | TS
| White Left Turn Arrow | Approved Materials Submittal Form | TS
| White Right Turn Arrow | Approved Materials Submittal Form | TS
Temporary Cold Plastic
| 8" White Cold Plastic | Approved Materials Submittal Form | TS
| White Right Turn Arrow | Approved Materials Submittal Form | TS
| White "ONLY" Text | Approved Materials Submittal Form | TS
Glass Beads
| Glass Beads | Certification | TS
Permanent Signing
Street Name Signs
| Ground Mounted Street Name Sign (Quivira) | Shop Drawings | TS
| Ground Mounted Street Name Sign (99th Ter) | Shop Drawings | TS
| Ground Mounted Street Name Sign (100th St) | Shop Drawings | TS
| Ground Mounted Street Name Sign (100th Ter) | Shop Drawings | TS
| Ground Mounted Street Name Sign (101st St) | Shop Drawings | TS
| Ground Mounted Street Name Sign (101st Ter) | Shop Drawings | TS
| Ground Mounted Street Name Sign (105th St) | Shop Drawings | TS
Advance Street Name Signs
| Advance Street Name Sign (99th St) | Approved Materials Submittal Form | TS
| Advance Street Name Sign (103rd St) | Approved Materials Submittal Form | TS
Standard MUTCD Signs
| Standard Signs | Catalog Cuts | TS
Sign Posts
| Sign Posts 1 3/4" x 1 3/4" x Var. | Approved Materials Submittal Form | TS
| Anchor 2" x 2" x 3' | Approved Materials Submittal Form | TS
| Sleeves 2 1/4" x 2 1/4" x 18" | Approved Materials Submittal Form | TS
| Sign Posts 2 1/2" x 2 1/2" x Var. | Approved Materials Submittal Form | TS
| Anchor 3" x 3" x 3' | Approved Materials Submittal Form | TS
Traffic Control
Standard MUTCD Signs
| Standard Signs | Catalog Cuts | TS
Channelizers
| Conical Delineators | Certification | TS
Barricades and Warning Lights
| Type I Barricades | Certification | TS
| Type II Barricades | Certification | TS
| Type III Barricades | Certification | TS
| Type A Flashers | Certification | TS
Message and Arrow Boards
| Flashing Arrow Panels | Certification | TS
| Portable Changable Message Signs | Certification | TS
T-Works Sign and Supports
| T-Works Sign | Certification | TS
| Sign Post | Certification | TS