## Read Me
Instructions:
Please use this form to submit Payment Requests to the Bureau of Local Projects.
To create a new tab for each pay request:
1.) | Go to the most recent "PR#nn" tab.
2.) | Press and hold "CTRL", click the current "PR#nn" tab with the mouse and drag to the right.
3.) | Double Click with mouse on the new tab and rename as appropriate. (PR#02, PR#03, etc.)
Light gray highlighted fields are for user input. All other fields will be computed and are locked.
+++++ Be sure to include invoicing details and 1010 forms with your submittal. +++++
A completed "Example" is included.
If you have any questions about this form, please contact Bill Legge at (785) 368-7397, wlegge@ksdot.org
Revision History:
| Rev01: | Added "Enter as a negative number." comments for "Less: …." cells.
| Rev02: | Changed title from "Payment Request" to "Payment Request Form".
Renamed "Contract Max" to "Project Max". This is used for over the max computation.
Added "Reimbursement Max" line to match agreement terminology. This is FYI.
Added DOT Form number to footer. (Number yet to be assigned.)
| Rev03: | Adjusted and renamed fields to aid input into CMS.
Changed "Less: Over the Max…." computation.
Added revision date and DOT Form number 1313 to footer.
Added conditional checks to compute CE funding availability.
| Rev04: | Added 2 CFR Part 200 language and signature block
| 9/2015 | Added additional adjustment lines
Revised CE Reimbursement line
Added "Contract Amount" field
Added "Must enter Begin and End dates!" warning
Added "LPA Invoice #" warning
Added alternative for entering a fixed local retainage amount
| 11/2015 | Changed retainage computation so that KDOT does not withhold retainage for payments
over the project max
Added liquidated damage computation capability
| 12/2015 | Changed retainage computation so that we only retain for particpating items.
Yes
No
Less: Liquidated Damages
Plus: Incentive

## Example
Payment Request Form
Date: |  |  |  | 2015-09-15
Project Description: |  |  |  | Geometric Improvements at Yellow Brick Road and Acme Street
KDOT Project #: |  |  |  | 106 N-5555-01 |  |  |  | CMS Contract #: | [5 empty] | 01716nnnn
LPA: |  | Emerald City | [7 empty] | LPA Project #: |  |  | TOTO123
LPA Invoice #: |  |  | XYZ123
Contract Amount: |  |  | 500000
Project Max: |  |  | 200000 |  |  |  |  | Reimbursement Max: |  |  |  |  | 160000 |  | to the LPA
Max KDOT Retainage: |  |  |  | 20000 |  |  |  |  | Computed Local Retainage: | [5 empty] | 29000
Work completed through: |  |  |  |  | Begin Date: |  |  | 2015-10-01 |  |  | End Date: |  |  | 2015-11-01
Final Invoice ? |  |  |  |  | No | FALSE
Total Costs Claimed | [14 empty] | 300000
Less: | Non-Participating | [13 empty] | -10000
0
Less: | Local Retainage |  |  |  | 10% |  | or Fixed Amount of | [6 empty] | 29000 | -20000
Subtotal | [14 empty] | 270000
Less: | Over the Max of the Contract | [13 empty] | -90000
Total Participating Cost | [14 empty] | 180000
KDOT/Federal Participation |  |  |  |  | 80% | [9 empty] | 144000
Less: | Local Participation |  |  |  | 20% |  | Prepaid Amount | [7 empty] | -36000
Less: | KDOT Retainage | [13 empty] | -500
Less: | Liquidated Damages: |  |  |  |  | 3 |  | days @ |  |  | 500 |  |  | per day | -1500
Less: | Previous Reimbursements | [13 empty] | -99500
AMOUNT DUE | [14 empty] | 42500
Previous Payments from KDOT | [14 empty] | 99500
Plus: Current Reimbursement from KDOT | [14 empty] | 42500
Total Reimbursement from KDOT | [14 empty] | 142000
Outstanding Reimbursements from KDOT | [14 empty] | 500
Total Reimbursement for CMS contract including pending payments | [14 empty] | 142500
*** Note: Invoice details must be submitted with invoice.***
By Signing this report, I certify to the best of my knowledge and belief that the report is true, accurate and the expenditures are for the purposes and objectives set forth in the terms and conditions of the Federal award. I am aware that any false, fictitious, or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise.
Certified by: | [11 empty] | Attest:
The Wizard of Oz | [11 empty] | Good Witch of the North
Note on P5: This will be provided to you by your KDOT PM.
Note on O6: If the LPA has assigned their own project number, enter it here or leave blank.
Note on E8: You will need to keep this up-to-date if any change orders are processed.
Note on G12: Select "Yes" or "No".
Note on S15: Enter as a Negative number.
Note on S23: Enter as a Negative number.
Note on S25: Enter as a Negative number.
Note on S33: Must have a Project Max AND be Final Invoice AND Local Retainage must be 0% to compute and display.
Note on A41: Change "Title1" as appropriate to person that has authority to make binding decisions for the LPA.
Note on N41: Change "Title2" as appropriate.

## PR01
Payment Request Form
Date:
Project Description:
KDOT Project #: | [6 empty] | CMS Contract #:
LPA: | [8 empty] | LPA Project #:
LPA Invoice #: | [5 empty] | Please enter an Invoice Number!
Contract Amount: |  | 0
Project Max: |  | 0 |  |  |  |  | Reimbursement Max: |  |  |  |  | 0 |  | to the LPA
Max KDOT Retainage: |  |  | 0 |  |  |  |  | Computed Local Retainage: | [5 empty] | 0
Work completed through: |  |  |  | Begin Date: | [5 empty] | End Date:
Final Invoice ? |  |  |  | No | FALSE |  | Must enter Begin and End dates!
Total Costs Claimed | [13 empty] | 0
Less: | Non-Participating | [12 empty] | 0
0
Less: | Local Retainage |  |  | 0% |  | or Fixed Amount of | [6 empty] | 0 | 0
Subtotal | [13 empty] | 0
Less: | Over the Max of the Contract | [12 empty] | 0
Total Participating Cost | [13 empty] | 0
KDOT/Federal Participation |  |  |  | 100% | [9 empty] | 0
Less: | Local Participation |  |  | 0% |  | Prepaid Amount | [7 empty] | 0
Less: | KDOT Retainage | [12 empty] | -500
Less: | Liquidated Damages: |  |  |  | 0 |  | days @ |  |  | 0 |  |  | per day | 0
Less: | Previous Reimbursements | [12 empty] | 0
AMOUNT DUE | [13 empty] | -500
Previous Payments from KDOT | [13 empty] | 0
Plus: Current Reimbursement from KDOT | [13 empty] | -500
Total Reimbursement from KDOT | [13 empty] | -500
Outstanding Reimbursements from KDOT | [13 empty] | 500
Total Reimbursement for CMS contract including pending payments | [13 empty] | 0
*** Note: Invoice details must be submitted with invoice.***
By Signing this report, I certify to the best of my knowledge and belief that the report is true, accurate and the expenditures are for the purposes and objectives set forth in the terms and conditions of the Federal award. I am aware that any false, fictitious, or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise.
Certified by: | [10 empty] | Attest:
Change as appropriate | [10 empty] | Change as appropriate
Note on P5: This will be provided to you by your KDOT PM.
Note on O6: If the LPA has assigned their own project number, enter it here or leave blank.
Note on E8: You will need to keep this up-to-date if any change orders are processed.
Note on G12: Select "Yes" or "No".
Note on S15: Enter as a Negative number.
Note on S23: Enter as a Negative number.
Note on S25: Enter as a Negative number.
Note on S33: Must have a Project Max AND be Final Invoice AND Local Retainage must be 0% to compute and display.
Note on A41: Change "Title1" as appropriate to person that has authority to make binding decisions for the LPA.
Note on N41: Change "Title2" as appropriate.