## Sheet1
Switzer (151st Street to 159th Street)
City Project NO. TH-0513
July 12-14, 2016
2 YEAR MAINTENANCE BOND INSPECTION PUNCH LIST
Median "E" Curb Between 151st Street and 153rd Street
Remove and replace curb at streetlight pole 15170 Southbound
Remove all of the old permanent signing
Median "E" Curb Between 153rd Street and 154th Street
Remove and replace curb 30' south of streetlight pole 15370 (x2) Northbound
Remove and replace curb 20' north of streetlight pole 15350 Northbound
Remove and replace curb 40' north of streetlight pole 15350 Northbound
Remove and replace curb between streetlight pole 15350 and pole 15350 Northbound
Remove and replace curb next to streetlight pole 15390 Northbound
Median "E" Curb Between 154th Street and 156th Terrace
| Remove and replace curb 50' south of streetlight pole 15410 Southbound | Remove all Stationing Stakes through out Phase I
Remove and replace curb next to streetlight pole 15410 Northbound
Median "E" Curb Between 156th Street/Terrace and 154th Street
Remove and replace curb/median nose at streetlight pole 15590, Northbound
Remove and replace curb 30' south of pole 15410 Northbound
Remove and replace curb 60' south of pole 15410 Northbound
Remove and replace curb 30' north of pole 15440 Northbound
Remove and replace curb between streetlight pole 15470 and pole 15500 Northbound
Remove pull ropes and flags from electrical boxes
Median "E" Curb Between 157th Terrace and 156th Terrace
Remove and replace curb 30' south of streetlight pole 15714 Northbound
Remove and replace curb 30' at streetlight pole 15714 Northbound
Remove and replace curb 50' north of streetlight pole 15714 Northbound
Remove and replace curb 30' south of streetlight pole 15688 Northbound
Remove and replace curb 40' south of streetlight pole 15688 Northbound
"A" and "B" Curb Northbound
Remove and replace "B" curb at the north wing of north driveway at 15609 Switzer
Remove and replace "B" curb for the north and south wings north of streetlight pole 15636
Remove and replace "B" curb 60' north of streetlight pole 15500 at the south wing
Remove and replace "B" curb 60' south of streetlight pole 15440
Remove and replace "A" curb at the southeast ramp at 154th Street
Remove and replace "B" curb north of 154th Street at the north wing
Remove and replace "B" curb 80' north of 154th Street
Remove and replace "B" curb 20' north of streetlight pole 15330
"A" and "B" Curb Southbound
NP-1 Crack 50' north of streetlight pole 15254
Remove and replace "B" curb 20' north of streetlight pole 15218
Remove and replace "B" curb 80' north of streetlight pole 15560
Remove and replace "B" curb south of driveway at 15430 Switzer
Remove and replace "A" curb at the northwest corner at 154th Street
Remove and replace "B" curb at the northwest corner at 157th Terrace
NP-1 Crack across from streetlight pole 15740
Remove and replace "A" curb at the southwest ADA ramp at 156th Terrace
Remove and replace "B" curb at the southwest corner at 157th Terrace
Remove and replace "B" curb 40' north of 157th Terrace
Driveways, ADA Ramps
Remove and replace at 15835 Switzer (driveway is Not Marked)
Remove and replace at 15523 Switzer (Mohomed)(driveway is Marked)
Regrout ramp at the northeast and southeast corners at 156th Street
Remove and replace and regrout ramps at the northeast and southeast corners at 154th Street
Remove and replace crack and regrout ramp at the northeast corner at 153rd Street
Regrout Ramp at the northwest corner of 156th Terrace
Remove and replace 2 panel at ADA ramp at the northwest corner at 157th Terrace
SE Corner 153rd Street Ramp
Sidewalk
Remove and replace sidewalk across from streetlight pole 15310 (starting to heave)
Use NP-1 (x2) across from streetlight pole 15370
Use NP-1 across from streetlight pole 15330
General Note:
1. Fix streetlight pole 15470 base plate (Electrical Cover)
Inspection completed on July 14, 2016
Scott Hobson
Construction Inspector Supervisor
City of Overland Park
(913) 233-9281
Note on A2: Scott Hobson:

## Printed
Switzer (151st Street to 159th Street)
City Project NO. TH-0496
2 YEAR MAINTENANCE BOND INSPECTION PUNCH LIST
Median "E" Curb Between 151st Street and 153rd Street
Remove and replace curb at streetlight pole 15170 Southbound
Remove all of the old permanent signing
Median "E" Curb Between 153rd Street and 154th Street
Remove and replace curb 30' south of streetlight pole 15370 (x2) Northbound
Remove and replace curb 20' north of streetlight pole 15350 Northbound
Remove and replace curb 40' north of streetlight pole 15350 Northbound
Remove and replace curb between streetlight pole 15350 and pole 15350 Northbound
Remove and replace curb next to streetlight pole 15390 Northbound
Median "E" Curb Between 154th Street and 156th Terrace
| Remove and replace curb 50' south of streetlight pole 15410 Southbound | Remove all Stationing Stakes through out Phase I
Remove and replace curb next to streetlight pole 15410 Northbound
Median "E" Curb Between 156th Street/Terrace and 154th Street
Remove and replace curb/median nose at streetlight pole 15590, Northbound
Remove and replace curb 30' south of pole 15410 Northbound
Remove and replace curb 60' south of pole 15410 Northbound
Remove and replace curb 30' north of pole 15440 Northbound
Remove and replace curb between streetlight pole 15470 and pole 15500 Northbound
Remove pull ropes and flags from electrical boxes
Median "E" Curb Between 157th Terrace and 156th Terrace
Remove and replace curb 30' south of streetlight pole 15714 Northbound
Remove and replace curb 30' at streetlight pole 15714 Northbound
Remove and replace curb 50' north of streetlight pole 15714 Northbound
Remove and replace curb 30' south of streetlight pole 15688 Northbound
Remove and replace curb 40' south of streetlight pole 15688 Northbound
"A" and "B" Curb Northbound
Remove and replace "B" curb at the north wing of north driveway at 15609 Switzer
Remove and replace "B" curb for the north and south wings north of streetlight pole 15636
Remove and replace "B" curb 60' north of streetlight pole 15500 at the south wing
Remove and replace "B" curb 60' south of streetlight pole 15440
Remove and replace "A" curb at the southeast ramp at 154th Street
Remove and replace "B" curb north of 154th Street at the north wing
Remove and replace "B" curb 80' north of 154th Street
Remove and replace "B" curb 20' north of streetlight pole 15330
"A" and "B" Curb Southbound
NP-1 Crack 50' north of streetlight pole 15254
Remove and replace "B" curb 20' north of streetlight pole 15218
Remove and replace "B" curb 80' north of streetlight pole 15560
Remove and replace "B" curb south of driveway at 15430 Switzer
Remove and replace "A" curb at the northwest corner at 154th Street
Remove and replace "B" curb at the northwest corner at 157th Terrace
NP-1 Crack across from streetlight pole 15740
Remove and replace "A" curb at the southwest ADA ramp at 156th Terrace
Remove and replace "B" curb at the southwest corner at 157th Terrace
Remove and replace "B" curb 40' north of 157th Terrace
Driveways, ADA Ramps
Remove and replace at 15835 Switzer (driveway is Not Marked)
Remove and replace at 15523 Switzer (Mohomed)(driveway is Marked)
Regrout ramp at the northeast and southeast corners at 156th Street
Remove and replace and regrout ramps at the northeast and southeast corners at 154th Street
Remove and replace crack and regrout ramp at the northeast corner at 153rd Street
Regrout Ramp at the northwest corner of 156th Terrace
Remove and replace 2 panel at ADA ramp at the northwest corner at 157th Terrace
SE Corner 153rd Street Ramp
Sidewalk
Remove and replace sidewalk across from streetlight pole 15310 (starting to heave)
Use NP-1 (x2) across from streetlight pole 15370
Use NP-1 across from streetlight pole 15330
General Note:
1. Fix streetlight pole 15470 base plate (Electrical Cover)
Note on A2: Scott Hobson: