151st Street (Pflumm Rd. to Antioch Rd.)

Utility Coordination Meeting Agenda

January 20, 2005

- Project Update

- Meeting Purpose

  - Verify location & easements for existing facilities

  - Determine relocation corridors for all utilities

  - Determine if any additional easements are necessary

  - Determine who needs a relocation agreement (with which City)

- Project Schedule					Pflumm to Quivira		Quivira to Antioch

a.	One Call 					(March, 2004)		(March, 2004)

b.	Initial Surveys ‘completed’ 			(April, 2004)			(April, 2004)

c.	Field Check Plans 				(November, 2004)		(November, 2004)

- Right-of-Way Plans/Legals 		(January, 2005)		(February, 2005)

- Next utility coordination meeting 		(February 17, 2005)		(February 17, 2005)

- Right-of-Way obtained 			(March-April, 2005)		(May, 2005)

- Begin utility relocations 			(February, 2005)		(May, 2005)

- Final Plans 					(February, 2005)		(November, 2005)

- Utilities must be clear 			(March 25, 2005)		(November, 2005)

- Begin Construction 				(April, 2005)			(January, 2006)

- End Construction 				(Spring, 2006)		(Fall, 2007)

4. 	Utility Roundtable Discussion:

Company		                  Contact			Phone Number

Water 1			Gordon Rames		(913) 895-5700

Southwestern Bell Telephone		Brent Ramirez		(913) 383-4884

KCP&L			Randy Jamison		(816) 245-3727

Kansas Gas Service			Chuck McAdams		(913) 599-8953

Time Warner Cable			Mario Escobar		(913) 643-1979

Johnson County Wastewater		Charles McAllister		(913) 681-3200

Blue Valley School District		Joe Yoakum			(913) 239-4117

Sprint			Brian George

Atmos Energy			Richard Yunghans		(913) 764-0531

Comcast Cable			Barbara Brown		(816) 795-2255

City of Olathe			Randy Freeman		(913) 971-9065

- Use Of Electronic Drawings & Color Utility Coordination Plans

- Discussion

CONFLICT COORDINATION: (Pflumm to Quivira)

| Location | Utilities Involved | Conflict/Resolution |
| --- | --- | --- |
| City of Olathe |  |  |
| Sta 49+75 to Sta 73+68, Lt. | 8” Water | Proposed relocation design by HNTB |
| JB #71 @ Sta. 100+98, Lt. | 8” Water | Conflict |
| CI # 70 @ Sta. 101+95, Lt. | 8” Water | Conflict |
| Water 1 |  |  |
| Sta 44+00 to Sta 49+45, Lt. (Quivira) | 2” Water | Under Pavement / Upgrade to 12” – relocate behind future storm sewer boxes |
| Sta 93+50 to Sta 97+00, Rt. | 8” Water | Conflict / Offset and lower under proposed sidewalk |
| Comcast | Overhead CATV | Coordinate with KCP&L Relocations |
| Sta 70+50, Lt. | CATV | Pedestal in sidewalk ramp |
| Sta 56+30 to 73+50, Lt. | CATV | Under Pavement |
| Sta 73+50, Lt. | Pedestal | In Pavement |
| TWC | Overhead CATV | Coordinate with KCP&L Relocations |
| Sta 48+26 to Sta 50+37, Rt. (Quivira) | CATV (F/O) | Under Pavement |
| Sta 100+33 to Sta 105+92, Rt. | CATV (dead) | Under Pavement |
| KCP&L |  |  |
| Sta 73+48 to Sta 86+41, Lt. | Underground | Under Pavement |
| Sta 73+48 to Sta 105+82, Lt. | Power Pole row | Conflict |
| Sta 86+41, Lt. | Light Pole | Conflict |
| Sta 44+26 to Sta 56+56, Rt. (Quivira) | Power Pole row | Conflict |
| Sta 51+79 to Sta 52+50, Rt. (Quivira) | Underground | Under Pavement |
| Sta 53+23, Rt. (Quivira) | Underground | Conflict |
| Atmos Energy |  |  |
| P-8A Crossing @ Sta 62+44, Rt. | 6” Gas | Vertical location? |
| Culvert Crossing @ Sta 80+34 | 6” & 2” Gas | Vertical location? |
| Sta 70+50 to Sta 71+50, Rt. | 6” Gas | 2’ Cut – vertical location? |
| Sta 76+00 to Sta 77+50, Rt. | 6” Gas | Conflict |
| CI #38 @ Sta 81+25, Rt. | 6” Gas | Conflict |
| CI #36 @ Sta 82+50, Rt. | 6” Gas | Conflict |
| Sta 87+50 to Sta 89+00, Rt. | 6” Gas | Conflict |
| CI #45,47,48,49,52, Rt. (Near Monrovia) | 4” Gas | Close! |
| Sta 93+50 to Sta 97+00, Rt. | 4” Gas | Conflict |
| P-62 Crossing @ Sta 98+94, Rt. | 4” Gas | Vertical location? |
| P-83 Crossing @ Sta 105+76, Rt. | 4” Gas | Vertical location? |
| Sta 52+16 to Sta 55+87, Rt. (Quivira) | 4” Gas | Under Pavement |
| CI #69 @ Sta 51+08, Rt. (Quivira) | 4” Gas | Conflict |
| CI #60 @ Sta 47+66, Rt. (Quivira) | 4” Gas | Conflict |
| Sta 42+44 to Sta 47+66, Rt. (Quivira) | 4” Gas | Conflict |
| SBC/Sprint |  |  |
| AI #3A @ Sta 56+70, Rt. | TEL/COM | Conflict |
| AI #5 @ Sta 59+70, Rt. | TEL/COM | Conflict |
| AI #8B @ Sta 62+45, Rt. | TEL/COM | Conflict |
| CI #15 @ Sta 69+70, Rt. | TEL/COM | Conflict |
| Sta 72+17, Rt. | Vault | In Pavement |
| Sta 85+83, Rt. | Vault | In Pavement |
| Sta 98+09, Rt. | Vault | In Pavement |
| Sta 101+68, Rt. | Vault | In Pavement |
| Sta 51+58, Rt. | Vault |  |
| Sta 53+11, Rt. | 2 Vaults |  |
| Sta 102+27, Rt. | Manhole | In Pavement |
| Sta 92+83, Lt. | Manhole | In Pavement |
| Sta 46+58, Rt. (Quivira) | Manhole | In Pavement |
| Sta 51+50 to Sta 72+00, Lt. | 2 Lines | Under Pavement |
| Sta 72+00 to Sta 73+48, Lt. | 3 Lines | Under Pavement |
| Sta 70+11 to Sta 72+00, Lt. | 1 Line | Conflict |
| Sta 73+48 to Sta 92+83, Lt. | 2 Lines | Under Pavement |
| Sta 92+83 to Sta 99+56, Lt. | 1 Line | Under Pavement |
| Sta 93+50 to Sta 97+00, Lt. | 1 Line | Conflict |
| Sta 99+56 to End of Project, Lt. | 2 Lines | Under Pavement |
| Sta 56+13 to Sta 67+85, Rt. | 2 Lines | Conflict |
| Sta 69+70 to Sta 91+27, Rt. | 2 Lines | Under Pavement |
| Sta 70+50 to Sta 71+50, Rt. | 1 Line | 2’ Cut – vertical location? |
| Sta 76+00 to Sta 77+50, Rt. | 1 Line | Conflict |
| Sta 87+50 to Sta 89+00, Rt. | 1 Line | Conflict |
| Sta 90+36 to Sta 93+79, Rt. | 1 Line | Conflict |
| Sta 91+27 to Sta 93+79, Rt. | 3 Lines | Under Pavement |
| Sta 93+79 to Sta 98+10, Rt. | 4 Lines | Conflict |
| Sta 98+10 to Quivira, Rt. | 5 Lines | Under Pavement |
| Quivira to End of Project, Rt. | 4 Lines | Under Pavement |
| Sta 46+58 to 151st St., Rt. (Quivira) | 1 Line | Conflict |
| 151st to Sta 58+00, Lt. (Quivira) | 2 Lines | Under Pavement |
| Sta 53+19 to 56+54, Rt. (Quivira) | 1 Line | Under Pavement |
| Executive Airport |  |  |
| Crossing @ Sta 60+65 | Electric | Install 4 x 4” Conduit Bank @ Sta 60+79 |

CONFLICT COORDINATION: (Quivira to Antioch)

| City of Olathe |  |  |
| --- | --- | --- |
| Sta 106+50 to Sta 126+74, Lt. | 8” Water | Conflict |
| CI #102 @ Harmony Ln. (E), Lt. | 8” Water | Conflict |
| Water One |  |  |
| Sta 110+50 to Sta 112+50, Rt. | 12” Water | Conflict |
| Sta 118+50 to Sta 123+00, Rt. | 12” Water | Conflict |
| Sta 126+74 to Sta 133+50, Lt. | 8” Water | Conflict |
| Sta 139+07 to Sta 143+50, Lt. | 8” Water | Conflict |
| AI #118 @ Melrose St. (S) | 6” Water | Conflict |
| 151st St. to Sta 11+40 (Stearns Pl.) | 4” Water | Conflict |
| Sta 150+00 to Sta 154+00, Lt. | 8” Water | Conflict |
| Sta 42+39 to Sta 57+00, Lt. (Switzer) | 8” Water | Conflict |
| Sta 50+48 to Sta 55+42, Lt. (Switzer) | 3” Water | Conflict |
| Sta 158+90 to 171+50, Lt. | 8” Water | Conflict |
| CI #175 @ Sta 172+89, Lt. | 8” Water | Close! |
| CI #178 @ Sta 175+70, Lt. | 8” Water | Close! |
| Sta 177+00 to Sta 182+50, Lt. | 8” Water | Conflict |
| Sta 186+17 to Sta 193+00, Lt. | 8” Water | Conflict |
| TWC | Overhead CATV | Coordinate relocation with KCP&L |
| Sta 105+90 to Sta 126+64, Rt. | CATV | Under Pavement |
| Sta 110+50 to Sta 112+50, Rt. | CATV | Conflict |
| Sta 118+50 to Sta 123+00, Rt. | CATV | Conflict |
| Crossing @ Sta 126+64 | CATV |  |
| Crossing @ Sta 133+10 | CATV |  |
| Sta 133+10 to Sta 139+80, Lt. | CATV | Under Pavement |
| Sta 138+00 to Sta 139+00, Rt. | CATV | Conflict |
| Crossing @ Sta 134+75 | CATV |  |
| Sta 134+75 to Sta 137+10, Rt. | CATV | Under Pavement |
| Crossing @ Sta 137+75 | CATV |  |
| Sta 152+51 to Sta 154+00, Lt. | CATV | Conflict |
| Crossing @ Sta 157+36 | CATV |  |
| Crossing @ Sta 48+01 (Switzer) | CATV | Conflict |
| Sta 48+01 to Sta 50+40, Lt. (Switzer) | CATV | Conflict |
| Crossing @ Sta 171+82 | CATV |  |
| Atmos Energy |  |  |
| Sta 110+50 to Sta 112+50, Rt. | 4” Gas | Conflict |
| Crossing @ Sta 110+41 | 2” Gas |  |
| Crossing @ Sta 116+91 | Service |  |
| Sta 118+50 to Sta 123+00, Rt. | 4” Gas | Conflict |
| Crossing @ Sta 119+00 | Service |  |
| Crossing @ Sta 119+53 | Service |  |
| Crossing @ Sta 128+94 | 2” Gas |  |
| Culvert crossing @ Sta 129+51 | 4” Gas |  |
| 151st St. to Sta 11+40 (Stearns Pl.) | 1 ¼” Gas | Conflict |
| Sta 138+00 to Sta 139+00, Rt. | 4” Gas | Conflict |
| Crossing @ Sta 139+88 | 2” Gas |  |
| Crossing @ Sta 153+66 | 4” Gas |  |
| Sta 150+50 to Sta 157+32, Rt. | 3” Gas | Conflict |
| Culvert crossing @ Sta 160+10 | 3” Gas |  |
| Crossing @ Sta 160+94 | Service |  |
| Crossing @ Sta 165+23 | Service |  |
| Sta 165+23 to Sta 166+59, Rt. | 3” Gas | Under Pavement |
| Crossing @ Sta 170+84 | Service |  |
| Crossing @ Sta 185+90 | 4” Gas |  |
| Sta 174+00 to Sta 182+50, Rt. | 3” Gas | Conflict |
| Kansas Gas Service |  |  |
| Sta 185+90 to Sta 198+38, Rt. | 2” Gas | Under Pavement |
| Crossing @ Sta 195+39 | 2” Gas |  |
| Crossing @ Sta 200+00 | 2” Gas |  |
| JCW |  |  |
| Misc. lid adjustments throughout project |  |  |
| Concrete encasement @ storm sewer crossings |  |  |
| KCP&L |  |  |
| Crossing @ Sta 126+66 |  |  |
| Crossing @ Sta 161+58 |  |  |
| Crossing @ Sta 181+79 |  |  |
| Crossing @ Sta 186+80 |  |  |
| Sta 108+45 to Sta 156+75, Lt. | Power Pole row | Conflict |
| Sta 156+37 to Sta 201+51, Rt. | Power Pole row | Conflict |
| Sta 171+81, Lt. | Power Pole | Conflict |
| Sta 41+56 to Sta 58+15, Lt. (Switzer) | Power Pole row | Conflict |
| SBC/Sprint |  |  |
| BOP to Stearns Pl., Rt. | 4 Lines | Under Pavement |
| Sta 110+50 to Sta 112+50, Rt. | 3 Lines | Conflict |
| Sta 118+50 to Sta 123+00, Rt. | 4 Lines | Conflict |
| Stearns Pl. to Switzer, Rt. | 2 Lines | Under Pavement |
| Sta 138+00 to Sta 139+00, Rt. | 2 Lines | Conflict |
| BOP to Sta 113+00, Lt. | 3 Lines | Conflict |
| Sta 115+65 to Sta 117+00, Lt. | 1 Line | Under Pavement |
| CI #96 @ Sta 119+20, Lt. | 2 Lines | Conflict |
| Sta 117+00 to Sta 123+40, Lt. | 3 Lines | Conflict |
| Sta 123+40 to Sta 128+00, Lt. | 2 Lines | Conflict |
| Sta 129+70 to Sta 133+00, Lt. | 1 Line | Under Pavement |
| Sta 133+00 to Sta 148+50, Lt. | 2 Lines | Under Pavement |
| Sta 144+43 to Sta 149+79, Lt. | 1 Line | Conflict |
| Sta 148+50 to Sta 149+50, Lt. | 1 Line | Under Pavement |
| Sta 150+00 to Sta 154+00, Lt. | 3 Lines | Conflict |
| Sta 150+50 to Sta 154+00, Rt. | 2 Lines | Conflict |
| Switzer to Sta 196+30, Rt. | 3 Lines | Under Pavement |
| Sta 174+00 to Sta 182+50, Rt. | 3 Lines | Conflict |
| Sta 196+30 to Sta 200+50, Rt. | 2 Lines | Under Pavement |
| Sta 200+50 to Sta 201+61, Rt. | 2 Lines | Conflict |
| Switzer to Sta 198+81, Lt. | 2 Lines | Under Pavement |
| Sta 163+00 to Sta 171+50, Lt. | 2 Lines | Conflict |
| Sta 177+00 to Sta 182+50, Lt. | 2 Lines | Conflict |
| Sta 189+50 to Sta 196+68, Lt. | 1 Line | Conflict |
| Sta 41+09 to Sta 42+96, Lt. (Switzer) | 1 Line | Conflict |
| Sta 42+96 to Sta 44+00, Lt. (Switzer) | 2 Lines | Conflict |
| Sta 48+30 to Sta 49+75, Lt. (Switzer) | 3 Lines | Conflict |
| Sta 49+75 to Sta 50+41, Lt. (Switzer) | 2 Lines | Conflict |
| Sta 50+41 to Sta 58+00, Lt. (Switzer) | 1 Line | Conflict |
| Sta 44+00 to Sta 48+25, Rt. (Switzer) | 4 Lines | Conflict |
| Sta 48+30 to Sta 49+65, Rt. (Switzer) | 2 Lines | Conflict |
| Sta 49+65 to Sta 51+33, Rt. (Switzer) | 1 Line | Conflict |
| Sta 51+33 to Sta 56+00, Rt. (Switzer) | 2 Lines | Conflict |