NOTE: Please review the notes below before listing any utility or entering any dates.
Kansas City Power & Light

4400 E. Front Street

Kansas City MO 64141	Electric	Rt.

Lt.

Rt.	0+809 to 2+589

2+589

5+010 to 5+070	X

X	X

X

X	10/30/98	Under

Construction	4/1/99

United Cities Gas

730 N. Ridgeview Rd.

Olathe, KS 66061	Natural Gas	Rt.

Rt.

Rt.	1+003 to 1+480

1+575 to 2+530

2+530 to 2+590	X

X

X	10/19/98	3/11/99	4/1/99
Southwestern Bell	9444 Nall

Overland Park KS 66207	Telephone

Lt.

Lt.

Lt./Rt.

Lt.

Lt./Rt.

Rt.

Rt.

Lt.

Lt.

Lt./Rt.

Lt.	Phase I Conflicts

2+605 to 1+410

1+520 to 1+410

1+410 to 1+360

1+410 to 1+040

1+040

1+040 to 1+020

1+020 to 4+900

1+040 to 1+020

1+020 to 5+210

1+020 to 0+860

Phase II

2+605 to 1+410

X

X

X

X

X

X

X

X

X

X

X	10/19/98

Under

Construction

After fill construction

4/15/99

30 Days
Time Warner Cable	PO Box 25567

Overland Park KS 66225	Cable TV	Rt.

Lt. To Rt.

Lt. To Rt.

Lt. To Rt.	1+522 to 2+589

1+522

2+178

2+589
X

X

X

X	Franchise Agreement	4/1/99	4/15/99
Water District #1

of Johnson County

7315 Frontage Road

Merriam KS 66204	Water

Phase II	Lt.

Lt.

Lt.

Lt.

Lt.

Lt.

Rt.

Lt./Rt.

Rt.

Lt.

Lt.

Lt.

Lt.	5+0.95 to 5+100 30’ Lt. CL 143rd

5+146 to 5+176 30’ Lt. CL 143rd

5+022 30’ Lt. CL 143rd

4+970 40’ Lt. CL 143rd

1+014( N. to 1+100( 51’ Lt. CL Quivira

1+320( N. to 1+490( 51’ Lt. CL Quivira

1+828( to 1+848( 70’ Rt. CL Quivira

2+180( to 2+230(

5+022( to 5+050( 45’ Rt. CL 137th

2+580( to 2+592( 51 Lt. CL Quivira

1+014( to 2+592( 32’ Lt. CL Quivira

2+230( N. to 2+580( 51’ Lt. CL Quivira

1+100( N. to 1+320( 51’ Lt. CL Quivira	X

X

X

X

X

X

X

X

X

X

X

10/27/98	Under

Construction

After grading and storm sewer are complete	4/1/99

4 to 6

weeks after

Johnson County Unified

Wastewater Districts	7311 W. 130th St., Suite 100

Overland Park KS 66213	Sanitary

Sewers	Rt.	1+750

1+853	X
N/A	To be performed by Roadway Contractor
Williams Pipeline Company	8001 College Boulevard

Suite 200

Overland Park, KS 66210	Petroleum Pipeline	Lt.

Lt.

Lt.

4+946 to 4+978

4+978 to 5+028

5+028 to 5+131	X

X

X

2/4/99	3/15/99	3/31/99
City of Olathe Water

K-7 and Spruce

Olathe, KS 66061	Water
Not in Conflict
Jones Intercable	4700 Selsa Road

P.O. Box 2000

Independence, MO 64055	Cable TV	Rt.	0+800 to 0+930
X	Franchise Agreement	4/1/99	4/15/99

Note:	If no utilities are within the limits of the project R/W, indicate NONE.	Submitted by:

USE ONLY actual calendar month, day, year. DO NOT use 30 days, 60 days, etc.

Utilities are to be moved as outlined under the KDOT BRUD Memo 84-10

Authorized City/County Official

Date

DOT Form 1304 – Revised 7/96

KANSAS DEPARTMENT OF TRANSPORTATION

BUREAU OF LOCAL PROJECTS

City/County:	City of Overland Park

Project Number:	46 N-0103-01

Name

of

Company

Address	Type

Utility

Lt.

Rt.

Sta. To Sta.

Private

R/W

Public

Agreement

Signed

Date

Estimated

Starting

Completion

Moves

Completed

LU-2

LIST OF UTILITIES AND STATUS OF SAME

Location

KDOT 1304 Utility Status

Mary Lou McCann

1999-05-11

Joe Archer

City of Overland Park