## HOME
DATA INPUT HOME
Project Information
County Name | JOHNSON
City Name | OLATHE
Project Number | 46 N-0748-01
Funding Program | CMAQ
Letting Date | 2024-01-17
Consultant | PAYNE-BROCKWAY
NOTE 1:
NOTE 2:

## RupisA-14mo
Kansas Department of Transportation
PROJECT SCHEDULE
Bureau of Local Projects (785) 296-3861
|  | Date Prepared: | 2023-09-25
|  | Prepared for: | City of OLATHE
|  | KDOT Project Number: | 46 N-0748-01
|  | Program: | CMAQ
|  | Current Tentative Letting Date: | 2024-01-17
NOTICE
The following dates are furnished as a guide to aid in maintaining this
project on a schedule which will insure the letting date indicated. The
letting date has been tentatively set and the amount of funds and/or the
obligation authority available could cause the schedule to be revised.
If the letting date is revised or the completion of the items fluctuate
significantly from the established dates listed, this schedule will be
revised to indicate the new tentative letting date and project schedule.
Plans forwarded to BLP will not be processed
without a current detailed estimate.
| ITEMS TO BE COMPLETED |  | Months to Letting | DEADLINE COMPLETION DATE | DATE COMPLETED -For Your Use Only-
| Consultant Design Contract to be Executed by |  | 14 | 2022-11-23
| Pre-Design Field Check |  | 12 | 2023-01-22
| Field Check Completed |  | 10 | 2023-03-23
| Office/ Final Check Plans & Estimate to BLP |  | 8 | 2023-05-22
| Office/ Final Check Plans Completed |  | 6 | 2023-07-21
| Begin CE Agreement |  | 6 | 2023-07-21
| R/W Clearances (1306 Form) to BLP |  | 4 | 2023-09-19
| Utility Form (1304 Form) to BLP |  | 4 | 2023-09-19
| Status of Permits (1307 Form) & Required Permits to BLP |  | 4 | 2023-09-19
| PS&E Plans to BLP |  | 3.5 | 2023-10-01
| PS&E Plans Completed |  | 1.5 | 2023-12-03
| Final Letting Plans to BLP |  | 1.2 | 2023-12-10
| CE Agreement Executed |  | 1.1 | 2023-12-13
| Advertise |  | 1 | 2023-12-18
cc: | PAYNE-BROCKWAY
| File |  |  |  | Rupis-A
2019-01-11

## RupisB-19mo
Kansas Department of Transportation
PROJECT SCHEDULE
Bureau of Local Projects (785) 296-3861
|  | Date Prepared: | 2023-09-25
|  | Prepared for: | City of OLATHE
|  | KDOT Project Number: | 46 N-0748-01
|  | Program: | CMAQ
|  | Current Tentative Letting Date: | 2024-01-17
NOTICE
The following dates are furnished as a guide to aid in maintaining this
project on a schedule which will insure the letting date indicated. The
letting date has been tentatively set and the amount of funds and/or the
obligation authority available could cause the schedule to be revised.
If the letting date is revised or the completion of the items fluctuate
significantly from the established dates listed, this schedule will be
revised to indicate the new tentative letting date and project schedule.
Plans forwarded to BLP will not be processed
without a current detailed estimate.
| ITEMS TO BE COMPLETED |  | Months to Letting | DEADLINE COMPLETION DATE | DATE COMPLETED -For Your Use Only-
| Consultant Design Contract to be Executed by |  | 19 | 2022-06-26
| Pre-Design Field Check |  | 17 | 2022-08-25
| Field Check Completed |  | 15 | 2022-10-24
| Office Check Plans & Estimate to BLP |  | 10 | 2023-03-23
| Office Check Plans Completed |  | 8 | 2023-05-22
| Final Check Plans & Estimate to BLP |  | 6 | 2023-07-21
| Begin CE Agreement |  | 6 | 2023-07-21
| Final Check Complete |  | 5 | 2023-08-20
| R/W Clearances (1306 Form) to BLP |  | 4 | 2023-09-19
| Utility Form (1304 Form) to BLP |  | 4 | 2023-09-19
| Status of Permits (1307 Form) & Required Permits to BLP |  | 4 | 2023-09-19
| PS&E Plans to BLP |  | 3.5 | 2023-10-01
| PS&E Plans Completed |  | 1.5 | 2023-12-03
| Final Letting Plans to BLP |  | 1.2 | 2023-12-10
| CE Agreement Executed |  | 1.1 | 2023-12-13
| Advertise |  | 1 | 2023-12-18
cc: | PAYNE-BROCKWAY
| File |  |  |  | Rupis-B
2019-01-11

## RupisC-22mo
Kansas Department of Transportation
PROJECT SCHEDULE
Bureau of Local Projects (785) 296-3861
|  | Date Prepared: | 2023-09-25
|  | Prepared for: | City of OLATHE
|  | KDOT Project Number: | 46 N-0748-01
|  | Program: | CMAQ
|  | Current Tentative Letting Date: | 2024-01-17
NOTICE
The following dates are furnished as a guide to aid in maintaining this
project on a schedule which will insure the letting date indicated. The
letting date has been tentatively set and the amount of funds and/or the
obligation authority available could cause the schedule to be revised.
If the letting date is revised or the completion of the items fluctuate
significantly from the established dates listed, this schedule will be
revised to indicate the new tentative letting date and project schedule.
Plans forwarded to BLP will not be processed
without a current detailed estimate.
| ITEMS TO BE COMPLETED |  | Months to Letting | DEADLINE COMPLETION DATE | DATE COMPLETED -For Your Use Only-
| Consultant Design Contract to be Executed by |  | 22 | 2022-03-28
| Pre-Design Field Check |  | 20 | 2022-05-27
| Field Check Completed |  | 15 | 2022-10-24
| Office Check Plans & Estimate to BLP |  | 11 | 2023-02-21
| Office Check Plans Completed |  | 9 | 2023-04-22
| Final Check Plans & Estimate to BLP |  | 6 | 2023-07-21
| Begin CE Agreement |  | 6 | 2023-07-21
| Final Check Complete |  | 5 | 2023-08-20
| R/W Clearances (1306 Form) to BLP |  | 4 | 2023-09-19
| Utility Form (1304 Form) to BLP |  | 4 | 2023-09-19
| Status of Permits (1307 Form) & Required Permits to BLP |  | 4 | 2023-09-19
| PS&E Plans to BLP |  | 3.5 | 2023-10-01
| PS&E Plans Completed |  | 1.5 | 2023-12-03
| Final Letting Plans to BLP |  | 1.2 | 2023-12-10
| CE Agreement Executed |  | 1.1 | 2023-12-13
| Advertise |  | 1 | 2023-12-18
cc: | PAYNE-BROCKWAY
| File |  |  |  | Rupis-C
2019-01-11