## CHANGE2
Project: | Nall Avenue - 143rd Street to 135th Street (TH-0624)
Owner: | City of Overland Park, Kansas
Note: For KDOT jobs, email Alison Bell, Adam Pritchard and Jeff Horton for approval prior to having contractor execute the change order. After the CO is fully executed, send a copy to Alison Bell via email for her files - per Jeff Horton 9/1/09.
Contractor: | APAC-Kansas, Inc.
7355 West 162nd Terrace
Overland Park, Kansas 66283
Contract Dated: November 15, 2004
In Accordance with the terms of the Contract referenced above, the CITY hereby authorizes the Contractor to make the following change to the Contract for the total additional amount of (insert dollar amount here). In all other respects, the terms and conditions of the (insert date of original agreement here) Agreement shall remain in full force and effect, except as specifically modified by this Change Order.
Estimated
|  |  | Unit | Additional | Additional
Item | Description | Unit | Price | Quantity | Payment
106 | Straw Bails | Ea. | 26.5 | 125 | 3312.5
107 | Additional Signal Modification (135th St) | Lump Sum | 20255 | 1 | 20255
108 | Temporary Detection Camera | Lump Sum | 3565 | 1 | 3565
|  |  | TOTAL this Change Order: |  | 27132.5
The work included in this Change Order does / does not require a time extension for this project. | [5 empty] | This statement is required by FHWA for monetary change orders as a result of audit on TH0852 on Nov. 18, 2009.
If a time extension is required a new completion date will need to be shown. See sample below:
Paragraph number 1 on page B-2 of the Bid, Article III on page A-2 of the Agreement, and section SC-24 item A. on page SC-7 of the Special Conditions shall be changed from completion of all work covered under this contract shall be completed by June 1, 2010 to all work covered under this contract shall be completed by June 14, 2010.
|  |  | Original Contract Amount: |  | 6483115.8
|  |  | Change Order #1 |  | 27132.5
Change Order #2
Change Order #3
|  |  | Revised Contract Amount: |  | 6510248.3
APPROVED BY:
CITY OF OVERLAND PARK, KANSAS
William D. Brown, Director of Public Works |  | Date | DPW can approve up to 10% of base contract with maximum of $50,000
Director of Public Works
John M. Nachbar |  | Date | CM can approve 10% of base contract - no maximum dollar amount
City Manager
Carl Gerlach |  | Date | Council must approve if it exceeds 10% over base contract amount
Mayor
ACCEPTED BY:
APAC - Kansas, Inc.
Contractor Representative |  | Date