PROGRESS MEETING AGENDA

QUIVIRA ROAD WIDENING (99TH STREET TO 105TH STREET)

OVERLAND PARK NO. TH-0948 –  JOHNSON COUNTY NO.  320000908 – KDOT NO. 46 N-0474-01

# Dennis Garrett Maintenance Facility Conference Room (11300 W. 91st Street)

# February 10, 2012 – 10:00 a.m.

- Contract Time Requirements

- Complete all Phase 1, 2A, 2B, 3, and 4 work and open all lanes to traffic by August 31, 2012.

- Complete all Phase 5 work and all Phase 1, 2A, 2B, 3, 4 and  5 punch list items by October 12, 2012.

- Liquidated Damages: $2,500/day, including weekends and holidays.

- Work Items Completed Since Last Meeting

- Work Items Scheduled Prior to Next Meeting

- Work Items From Contractor Construction Schedule Approved on February 6, 2012

- Last Week  - Phase 1 Traffic Signals (subsurface).  Phase 1 (SB) Install storm sewer.

- This Week – Phase 1 Traffic Signals (subsurface).  Install storm sewer, clearing & grubbing, rough grading and removals. Fly Ash, irrigation, monuments.

- Next Week – Phase 1 Traffic Signals (subsurface).  Clearing, grubbing, rough grading & removals.  Fly Ash, Edge drain.

- Utility Relocations

- KCPL poles - Last poles (2) to be removed after signals switched over – 99th & 103rd.

- WaterONE - Remaining priorities.

- West 103rd Street

- Cleanup West 101st Terrace

- NE corner East 103rd Street

- West 105th Street

- East 105th Street

- Sta 104+40

- Cleanup

- AT&T conflict?

- Contractor Submittals

- Three copies of all submittals

- Asphalt – need resubmittal as discussed – Tony has contacted O’Donnell.

7.	Erosion and Sediment Control

- Inspections every 7 days and after 0.5 inch rain event.

8.	Outstanding Issues/Concerns

- Miles Excavating, Inc.

- HNTB Corporation

- The City of Overland Park, KS – Inspectors

- The City of Overland Park, KS – Project Manager

- Updated schedule? – need to reflect phase change and possible delay from traffic signal order.

- Force Account Items – Approved 1,2,3,6.  Need 4 and 5.

- Monument reconstruction

- Forms to KDOT prior to payment