## Sheet1
PROJECT STATUS REPORT
CIP Number TH-0303 & TH-0303A
Project Description: Antioch, 143rd to 151st Street
1999-07-21 11:32
36362.4804
| Total Estimated | Total Paid | Total Estimated
| Costs | To Date | Balance
Design Team Through 12-31-97 (TH-0303) | 72622 | 72622 | 0
Engineering (TH-0303) | 246300 | 246300 | 0
Construction | 2189822.03 | 2189822.03 | 0
Relocate Utilities | 86982 | 86982.29 | -0.29
Operating Equipment | 1048 | 1047.96 | 0.04
Testing/Drilling | 13544 | 13544 | 0
Publications/Misc/Filing Fees | 4591 | 4591.35 | -0.35
Appraisers Fees | 25125 | 25125 | 0
Ownerships | 8125 | 8125 | 0
Right of Way Awards | 69030 | 69030 | 0
Easements | 29873 | 29873 | 0
Temporary Note Interest | 0 | 0 | 0
Cost of Issuing Temporary Notes | 0 | 0 | 0
Bonding Costs | 0 | 0 | 0
Total Project Costs | 2747062.03 | 2747061.63 | 0.4
Interest earned | 4865
Excise Tax | 1821500
Escrow | 559192
Cap Impr Fund (PAYG) | 361505.03
Total Funding | 2747062.03
-All expenses as of 7-12-99.
-This worksheet combines TH0303 and TH0303A, design engineering and construction.
-All escrows on Antioch have been rolled out. See list. Amounts rolled out were more than amounts
shown on this list.
-CIP Budget showed County funds. However, there were no CARS funding for this project, per Wayne G
-No PAYG funding has been used on this project to date. CIP Budget showed $481,880 for TH0303A.
$400,000 was used on the TH0303A (design)
-Divided Design Engineering (TH-0303) into Design Team Through 12-31-97 (TH-0303) and Engineering (TH-0303).