## Sheet1
COLLEGE BLVD (PFLUMM ROAD TO U.S. - 69)
City Project NO. TH-0852 KDOT Project NO. 46N-0373-01
2 YEAR MAINTENANCE BOND INSPECTION PUNCH LIST
Pflumm to Hauser (Median)
Remove and replace curb eastbound at street light pole 13310
| Fix brick settlement between streetlight pole 13418 and Pflumm | General notes
| Remove and replace asphalt stripping eastbound at Pflumm match point | Remove all of the old permanent signing
Pflumm to Hauser (Outsides)
| Remove and replace curb at the southwest corner of Hauser and College | Remove all Stationing Stakes through out Phase I
| Remove and replace curb eastbound across from streetlight pole 13346 | Remove pull ropes and flags from electrical boxes
Hauser to Westgate (Median)
Remove and replace curb eastbound, east of street light pole 13205
Hauser to Westgate (Outsides)
Remove and replace curb at the northeast corner of entrance to "The Crossings"
Remove and replace curb at the southwest corner of Westgate and College
Remove and replace concrete entrance southwest corner of Westgate and College
Remove and replace curb eastbound, east of streetlight pole 12865
Remove and replace curb westbound at the northwest corner of Hauser and College
Remove and replace ADA brick/grout at the northwest corner of Hauser and College
Remove and replace curb westbound across from streetlight pole 13120
Westgate to Oakmont (Median)
Remove and replace curb eastbound/westbound between streetlight pole 12350 and Oakmont (X9)
Fix settled brick at the west nose at Oakmont
Remove and replace curb eastbound, east of streetlight pole 12390
Remove and replace curb eastbound at east median nose
Westgate to Oakmont (Outsides)
Backfill settlement westbound across from streetlight pole 12390 to streetlight pole 12350
Remove and replace curb eastbound across from streetlight pole 12350
Backfill settlement eastbound across from streetlight pole 12390
Remove and replace curb eastbound across from streetlight pole 12390 at curb inlet
Remove and replace curb eastbound across from streetlight pole 12470
Remove and replace sidewalk at the southeast corner of Westgate and College and backfill settlement back of curb
Backfill settlement at the northeast corner of Westgate and College
Remove and replace sidewalk at the northeast corner of Westgate and College
Remove and replace curb at the northeast corner of Westgate and College at curb inlet
Oakmont to Quivira (Median)
Remove and replace curb eastbound/westbound between streetlight poles 11986 and 12024 (x3)
Remove and replace curb eastbound/westbound at streetlight pole 11986
Remove and replace cueb eastbound/westbound between streetlight poles 11986 and 11948 (x6)
Remove and replace curb eastbound/westbound between streetlight poles 11948 and 11910 (x8)
Remove and replace curb westbound at streetlight pole 11910
Remove and replace curb eastbound/westbound between streetlight poles 12176 and 12214 (x5)
Remove and replace curb eastbound/westbound at streetlight pole 12214 and streetlight pole cap
Remove and replace curb eastbound/westbound between streetlight poles 12214 and 12252 (x7)
Remove and replace curb westbound at streetlight pole 12252 and streetlight pole cap
Remove and replace curb eastbound/westbound between streetlight poles 12252 and 12292 (x7)
Oakmont to Quivira (Outsides)
Remove and replace sidewalk at the entrance to Waterway Car Wash
| Remove and replace curb at the entrance to Waterway Car Wash | Remove dirt spoils from the southeast corner of 112thstreet and Metcalf
Remove and replace curb at the entrance to Metcalf Bank (x2)
North Leg of Oakmont
Backfill settlements northbound at the entrance
Reset brick east median nose at Grant and 143rd street
Crack seal/fix asphalt northbound/southbound
South Leg of Oakmont
Crack seal
Quivira to Cody/112th Street (Median)
Remove and replace curb at streetlight pole 11890 (x4)
Remove and replace curb between streetlight poles 11890 and 11884 (x8)
Remove and replace curb at streetlight pole 11846 (x2)
Remove and replace curb between streetlight poles 11846 and 11800 eastbound/westbound (x12)
Remove and replace streetlight pole base at 11800
Remove and replace curb between streetlight pole 11800 and brick header (x4)
Remove and replace curb westbound, west of streetlight pole 11755
Quivira to Cody/112th Street (Outsides)
Remove and replace curb at the northeast and northwest corners of entrance to "College Village"
Crack seal entrance to "College Village"
Remove and replace curb eastbound across from streetlight pole 11846
Remove and replace curb at the southeast corner of College and Quivira
Crack seal northeast area of College and Quivira
Remove and replace curb westbound, east of the northeast corner of College Quivira
Remove and replace curb at the northeast/northwest corners of the entrance to "College Oaks Office Park"
Remove and replace curb westbound across from streetlight pole 11755 50' to the west
South Leg of 112th Street
Crack seal
Remove and replace curb north end of median
Remove and replace curb at the southwest corner of 112th street and College
Cody/112th Street to King (Median)
Remove and replace curb westbound between streetlight poles 11310 and 11386
Cody/112th Street to King (Outsides)
Remove and replace curb eastbound, east of streetlight pole 11614
Remove and replace curb at the southeast corner of 112th Street and College
Remove and replace curb inlet throat westbound across from streetlight pole 11614
Remove and replace curb east of streetlight pole 11614 westbound
Remove and replace curb westbound, west of streetlight pole 11462
Remove and replace sidewalk and signal pole cap at the northwest corner of King and College
Remove and replace curb at the southewest corner of King and College
Remove and replace signal pole cap at the southwest corner of King and College
Remove and replace curb eastbound across from streetlight pole 11386
King to Nieman (Outsides)
Remove and replace curb east entrance to College Parks next to Holtz's Hotel
Remove and replace sidewalk and curb at the northeast corner of King and College
Crack seal north leg of King
Remove and replace curb at curb inlet westbound, west of streetlight pole 11155
Remove and replace sidewalk ramp at the northwest corner of Nieman and College
Crack seal north leg of Nieman
Remove and replace sidewalk at signal pole, southwest corner of Nieman and College
Remove and replace eastbound, east of streetlight pole 11155
South Leg of Nieman
Remove and replace approach slab at field entrance
Crack seal roadway, northbound and southbound
Remove and replace curb curb inlet northbound 60' north of creek
Remove and replace curb inlet throat and curb at creek northbound
Remove and replace curb south of streetlight pole 11265, northbound
Crack seal 113th Street to match point
Remove and replace curb inlet throat southbound at 11264 Nieman
Remove and replace curb at entrance to Marbella Condominiums
Remove and replace curb at the southeast corner of Nieman and College
Remove and replace curb south of streetlight pole 11147, northbound
Remove and replace curb north of field entrance, northbound
Nieman to Switzer (Medians)
Remove and replace curb between streetlight poles 11090 and 11020 eastbound/westbound (x4)
Remove and replace curb at streetlight pole 11090 eastbound/westbound (x2)
Remove and replace curb between streetlight poles 11020 and 10950 (x3)
Remove and replace curb westbound, east of streetlight pole 10950
Remove and replace curb westbound at streetlight pole 10740
Nieman to Switzer (Outsides)
Remove and replace curb westbound across from streetlight pole 10950 at curb inlet
Remove and replace curb at the northwest corner of 109th Street and College
Remove and replace sidewalk at the northwest corner of 109th Street and College
Crack Seal median, north leg of 109th Street
Remove and replace sidewalk at the northeast corner of 109th Street and College
Remove and replace curb/curb inlet throat, eastbound, east of streetlight pole 10530
Remove and replace curb eastbound across from streetlight pole 10600
Remove and replace curb eastbound, east of streetlight pole 10740
Remove and replace curb at the southeast corner of Nieman and College
Remove and replace sidewalk westbound, west of of streetlight pole 11020
Remove and replace curb westbound across from streetlight pole 11020
General Note: Eastbound and Westbound College will require crack sealing as needed
Inspection completed during the month of May 2012
Scott Hobson
Construction Inspector Senior
City of Overland Park
(913) 233-9281
Note on A2: Scott Hobson: