{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["CHANGE2"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"CHANGE2","index":0,"n_rows":61,"n_cols":8,"rows_kept":61,"merged":[[4,7,7,12],[11,1,11,6],[22,7,22,12]],"flags":["formulas_cached_only"]}
[]
[null,"Project: Nall Avenue, 143rd Street to 135th Street"]
[]
[null,"Owner:  City of Overland Park, Kansas"]
[{"$nulls":7},"Note:  For KDOT jobs, email Alison Bell, Adam Pritchard and Jeff Horton for approval prior to having contractor execute the change order.  After the CO is fully executed, send a copy to Alison Bell via email for her files - per Jeff Horton 9/1/09. mlm"]
[null,"Contractor: APAC-Kansas, Inc."]
[null,"                  7355 West 162nd Terrace"]
[null,"                  Overland Park, Kansas  66283"]
[]
[null,"Contract Dated: November 15, 2004"]
[]
[null,"In Accordance with the terms of the Contract referenced above, the CITY hereby authorizes the Contractor to make the \nfollowing change to the Contract for the total additional amount of $______________ .  In all other respects, the terms and conditions of the (insert date of original contract) Agreement shall remain in full force and effect, except as specifically modified by this Change Order."]
[]
[]
[{"$nulls":5},"Estimated"]
[{"$nulls":4},"Unit","Additional","Additional"]
[null,"Item","Description","Unit","Price","Quantity","Payment"]
[null,106,"Straw Bails","Ea.",{"v":26.5,"d":"26.50"},125,{"v":3312.5,"d":"3,312.50"}]
[null,107,"Additional Signal Modification (135th St) ","Lump Sum",{"v":20255,"d":"20,255.00"},1,{"v":20255,"d":"20,255.00"}]
[null,108,"Temporary Detection Camera","Lump Sum",{"v":3565,"d":"3,565.00"},1,{"v":3565,"d":"3,565.00"}]
[]
[]
[null,"The work included in this Change Order does / does not require a time extension for this project.",{"$nulls":5},"Required by FHWA as a result of audit on TH0852 on Nov. 18, 2009."]
[null,"If a time extension is required a new completion date will need to be shown."]
[]
[]
[{"$nulls":4},"TOTAL this Change Order:",null,{"v":27132.5,"d":"27,132.50"}]
[]
[{"$nulls":4},"Original Contract Amount:",null,{"v":6483115.8,"d":"$6,483,115.80"}]
[]
[{"$nulls":4},"Additions to Date:",null,{"v":27132.5,"d":"$27,132.50"}]
[{"$nulls":4},"  Change Order #1",null,{"v":27132.5,"d":"$27,132.50"}]
[{"$nulls":4},"  Change Order #2"]
[{"$nulls":4},"  Change Order #3"]
[]
[{"$nulls":4},"Revised Contract Amount:",null,{"v":6510248.3,"d":"$6,510,248.30"}]
[]
[null,"APPROVED:"]
[]
[null,"CITY OF OVERLAND PARK, KANSAS"]
[]
[]
[]
[null,"William D. Brown, Director of Public Works",null,"Date","DPW can approve up to 10% of base contract with maximum of $50,000"]
[null,"Director of Public Works"]
[]
[]
[null,"John M. Nachbar",null,"Date","CM can approve 10% of base contract - no maximum dollar amount"]
[null,"City Manager"]
[]
[]
[null,"Carl Gerlach",null,"Date","Council must approve if it exceeds 10% over base contract amount"]
[null,"Mayor"]
[]
[null,"ACCEPTED:"]
[]
[null,"APAC - Kansas, Inc."]
[]
[]
[]
[null,"Contractor Representative",null,"Date"]