{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":39,"n_cols":12,"rows_kept":39,"flags":["formulas_cached_only"]}
[{"$nulls":4},"OVERLAND PARK"]
[]
[{"$nulls":3},"CITY ADMINISTERED PROJECTS"]
[]
[null,"FIELD ","ENV CLR","FINAL PLAN","SICK-STE","PS&E","AUTH TO","LETTING","AUTH TO","LOW","CONTRACT","DBE"]
[null,"CHECK","TO","APPROVAL","APPROVAL","OBLIG","BID","DATE","AWARD","BID","BOND","GOAL"]
["PROJECT","PLANS","CITY",2,3,"DATE",4," ","4A",5,6,7]
["N-0103","1998-06-23","1999-03-15","1999-04-01","1999-03-10","1999-03-18","1999-03-18",null,"1999-04-27","1999-05-24","1999-05-24","1999-05-25"]
["N-0117","1998-12-14","1999-12-13",{"$nulls":4},"(1/1/00)"]
["N-0131","1999-01-28","1999-08-18",null,null,"1999-09-27"]
["N-0132","1999-03-03",{"$nulls":3}," "," ","(2/8/00)"]
["N-0149"]
["N-0152","1999-05-07","1999-06-02","1999-10-13","1999-10-05","1999-09-27","1999-10-13","11/16/99","1999-11-30","1999-11-30"]
["N-0153","1999-05-12","1999-06-02","1999-10-13","1999-10-05","1999-09-27","1999-10-13","11/16/99","1999-11-30","1999-11-30"]
["N-0154","1999-05-07","1999-09-10","1999-10-19","1999-10-19","1999-09-28","1999-10-19","(12/99)"]
["N-0155","1999-05-07","1999-09-10","1999-10-19","1999-10-19","1999-09-28","1999-10-19","(12/7/99)"]
["N-0165","1999-07-29","1999-09-16","1999-10-19","1999-10-19","1999-09-14","1999-10-19","(12/7/99)"]
["N-0168"]
["N-0169"]
{"$rows_empty":12}
["Letter/memo","          PURPOSE",{"$nulls":5},"PREREQUISITE"]
[2,"Final plan approval",null,"Final plans & estimate, Des Sum Doc, R/W & utility clearance, CE estimate, bid proposal"]
[3,"Approval to authorize",null,"Final plans, specifications, & special provisions, date of memo to Sick"]
[4,"Authorize to bid",null,"PS&E approval  (PSEI, DOT 130 APPRVL screen on CPMS)"]
["4A","Authority to award",null,"Satisfactory low bid"]
[5,"Low bid to Ehmen",null,"Satisfactory low bid with bid tab"]
[6,"Bid documents to Ehmen",null,"Signed contract, contractor bond, cost breakdown for FHWA"]
[7,"DBE goals",null,"DBE contract goals and total bid amount"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}