## after bid
|  | Project Totals | CARS Eligible
1 | Construction Cost * | 3428323.42 | 3428323.42
| Contractor Bid | 3234700.5 | 3234700.5
| Interim Irrigation Modifications | 4202.92 | 4202.92
| LED Kits | 30503 | 30503
| Traffic Signal Poles | 51917 | 51917
| Estimated Riley Traffic Signal Cabinet and Controller | 7000 | 7000
| Estimated Early Incentive Bonus | 100000 | 100000
2 | Estimated Change Orders (3% Of Contractor Bid) | 97041.015 | 97041.015
3 | Engineering
| Final Design (TH-0019 funding) | 347640
| Consultant EDC (TH-0019 funding) | 21560 | 21560
| City Inspection (if Federal/CARS/SMAC/Other Cities Eligible) | 130000 | 130000
4 | Material Testing | 7157 | 7157
5 | Project Administration | 50000
6 | Legal Publications, Blueprinting, Miscellaneous | 25000
7 | Ownership Certificates/Title Report | 6775
8 | R/W & Easement Acquisition | 63740
| Negotiation | 31240
| Estimated Condemnation | 30000
| Legal Fees | 2500
9 | Utility Relocations | 84290.67
| Kansas City Power & Light Company | 59890.67
| Water District No. 1 | 24400
| Total Project Cost | 4261527.105
| CARS Share (50% of CARS Eligible Items)** | 1842040.7175
| City Cost Share | 2419486.3875
| City Cost Share with City Inspection and Project Administration Removed | 2239486.3875
Budget:
| Design - TH-0019 (2001-2005 Adopted CIP Dated August 14, 2000) | 370591 | PAYG
| Construction - TH-0019A (2003-2007 Proposed CIP Dated December 3, 2001) | 3020335 | 1/8STX
| Construction - TH-0019A (2003-2007 Proposed CIP Dated December 3, 2001) | 56745 | UESC
| City Funding | 3447671
| Construction - TH-0019A (2003-2007 Proposed CIP Dated December 3, 2001) | 2035000 | CTY
| Other Funding | 2035000
| Total Budget | 5482671
| Under Budget (City Funding minus City Cost Share with Insp and Admin Removed) | 1208184.6125
* Based on contractor bid plus any other contract costs
** CARS cap is $2,035,000