PROGRESS MEETING AGENDA

119TH STREET WIDENING (U.S. 69 TO RILEY)

CITY PROJECT NO. TH-0734 – KDOT PROJECT NO. 46 N-0366-01

Overland Park Fire Training Center

# April 15, 2008 – 1:30 p.m.

- Contract Time Requirements

- Complete all Phase 1, 2 and 3 work and open all lanes to traffic by October 15, 2008.

- Complete all Phase 4 restoration work (lawn sprinkler system, landscape restoration, sod and permanent seeding) and all Phase 1, 2, 3 and 4 punch list items by November 15, 2008.

- Work Items Completed Since Last Meeting

- Work Items Scheduled Prior to Next Meeting

- Work Items From Contractor Construction Schedule Approved on March 12, 2008

- Last Week – continue installing storm drainage / inlets / pipes, begin subgrade preparation / fly ash, complete eastbound outside lane widening tear out, complete installing storm drainage / inlets / pipes, begin subgrade preparation / fly ash, continue installing traffic signals for outside widening, continue north Antioch tear out / replace, begin north Grant tear out / replace, complete Pinnacle Village tear out / replace, begin south Access Road tear out / replace

- This Week – complete installing storm drainage / inlets / pipes, continue subgrade preparation / fly ash, begin installing edge drain, complete subgrade preparation / fly ash, complete installing edge drain, continue installing traffic signals for outside widening, complete north Antioch tear out / replace, complete north Grant tear out / replace, begin north Farley tear out / replace, complete south Access Road tear out / replace, begin south Lowell tear out / replace, begin south Fire Station entrance tear out / replace

- Utility Relocations

- Contractor Submittals

7.	Erosion and Sediment Control

8.	Outstanding Issues/Concerns

- Miles Excavating, Inc.

- HNTB Corporation

- The City of Overland Park, KS – Inspectors – Discuss dumping fly ash.

- The City of Overland Park, KS – Project Manager – Submit signed copies of each subcontract.  Discuss integral sidewalk and retaining walls.