PROGRESS MEETING MINUTES

119th STREET WIDENING (US 69 TO RILEY)

CITY PROJECT NO. TH-0734 – KDOT PROJECT NO. 46 N-0366-01

Overland Park Fire Training Center

April 15, 2008 – 1:30 p.m.

Attendance: Wayne Gudenkauf ( City of Overland Park )

Alan Daniels ( City of Overland Park )

John Yoakum ( HNTB )

Butch Adams ( Miles Excavating )

Mario Escobar ( Time Warner Cable )

- Contract Time Requirements:

- Complete all Phase 1, 2 and 3 work and open all lanes to traffic by October 15, 2008.

- Complete all Phase 4 restoration work ( lawn sprinkler system, landscape restoration, sod and permanent seeding) and all Phase 1, 2, 3 and 4 punch list items by November 15, 2008.

- Work Items Completed Since Last Meeting

  - Pumped out water holes

  - Landsworks completed Interim Sprinkler System on South Side of 119th

  - Storm Sewer has been started

  - Tear out is still ongoing

  - Signals at Lowell

  - Moved Signal base South of Sidewalk on NW corner of Lowell

- Work Items Scheduled Prior to Next Meeting

  - Tear out

  - Signals at Lowell and Hardy

  - Grade Fly Ash

  - Junction Box Tops to be Started

  - Storm Sewer

- Work Items from Contractor Construction Schedule Approved on March 12, 2008

  - Last Week – continue installing storm drainage / inlets / pipes, begin subgrade preparation / fly ash,  complete eastbound outside lane widening tear out, complete installing storm drainage / inlet / pipes, begin subgrade preparation / fly ash, continue installing traffic signals for outside widening, continue north Antioch tear out / replace, begin north Grant tear out / replace, complete Pinnacle Village tear out / replace, begin south Access Road tear out  / replace

  - This Week –complete installing storm drainage / inlets / pipes, continue subgrade preparation / fly ash, begin installing edge drain, complete subgrade preparation / fly ash, complete installing edge drain, continue installing traffic signals for outside widening, complete north Antioch tear out / replace, complete north Grant tear out / replace, begin north Farley tear out / replace, complete south Access Road tear out / replace, begin south Lowell tear out / replace, begin south Fire Station tear out / replace

- Utility Relocations

  - AT&T Long-distance – Complete

  - AT&T Local – need to relocate 50 pair line at SE corner of Hardy, to relocate service drops at station 247+50 Rt., start restoration

  - Time Warner – Splicing scheduled for 4-15-08 at night, Hemlock scheduled with contractor tear out, pedestal to be removed at SE corner of Antioch with Perm. Signals, switch over everything overhead by 4-16-08

  - Kansas Gas Service – Antioch lines to be completed during roadwork

  - KCPL – Complete

  - Everest  - Complete

  - Johnson County Wastewater – No conflict

  - Atmos Gas – Complete

  - Blue Valley School District – In contract to relocate

  - City of Overland Park – In contract to relocate

  - Water One – Complete

- Contractor Submittals

  - Traffic signals submittals still in progress

- Erosion And Sediment Control

  - Silt fence at all sump inlets and up stream from all inlets

  - Silt fence around most inlets

  - Straw wattles have been placed

- Outstanding Issues/Concerns

  - Miles Excavating, Inc.

Wants to shut down a lane of traffic early to dump and spread fly ash during minimal traffic, spread fly ash with a Motor Grader, shut down either east or west of Antioch for Fly Ash dumping.

- HNTB Corporation

Shop drawings for Structure #9

Structure #9 from Modified Curb Inlet to a Junction Box to a 4 x 4 Junction Box

Various plan errors pointed out

- The City of Overland Park, KS – Inspectors

Fly ash dumping to see if it would be possible to have belly dumps

- The City of Overland Park, KS – Project Manager –Submit signed copies of each subcontract. Discuss integral sidewalk and retaining walls.