## Sheet1
159th Street (Quivira Road to Antioch Road)
City Project No. TH-0870
KDOT Project No. 46 N-0539-01
CARS Project No. 320000925
|  | SUBMITTAL CHECKLIST |  |  |  | 2018-02-09
|  |  | Primary | Buy Amer. | Date | Date | Date
Item | Description | Submittal | Reviewer | Certified | Submitted | Reviewed | Approved
Subcontractor List
| Original Subcontractor List | List | PM
Construction Schedule
| Original Construction Schedule | Schedule | PM
Construction Video
| Preconstruction | Video IAW The Specifications | PM
| Post Construction | Video IAW The Specifications | PM
Soil
|  | Moisture - Density Relationship | PM
Aggregates
| Temporary Surfacing Material (AB-3 OP Modified) | KDOT Type B Certification | CI
| Base for Bike Path (AB-3 OP Modified) | KDOT Type B Certification | CI
| Aggregate (57 Rock) Supplier | KDOT Type B Certification | CI
| Aggregate (57 Rock) Supplier | KDOT Type B Certification | CI
| Aggregate (UD-1) | KDOT Type B Certification | CI
| Aggregate (BD-1) | KDOT Type B Certification | CI
| Aggregate (PB-2) | KDOT Type B Certification | CI
| Aggregate Base Course (OP Special) | KDOT Type B Certification | CI
Asphalt
| Asphaltic Concrete (Surface Course) | Mix Design | PM
| Asphaltic Concrete (Intermediate Course) | Mix Design | PM
Sidewalk 4K Concrete
| KCMMB Miles (Supplier) Mixes 860022,860024 | Mix Design | CI
| KCMMB Miles (Supplier) All Mixes | Mix Design | CI
| Expansion Material | KDOT Type D Certification | CI
| Liquid Membrane-Forming Compounds (Curing Compound) | KDOT Type C Certification | CI
Sidewalk Ramps
| KCMMB Miles (Supplier) Mixes 860022,860024 | Mix Design | CI
| KCMMB Miles (Supplier) All Mixes | Mix Design | CI
| Expansion Material | KDOT Type D Certification | CI
| Liquid Membrane-Forming Compounds (Curing Compound) WCI | KDOT Type C Certification | CI
| Reinforcing Steel (Epoxy) Grade 40 | KDOT Type B Certification | CI
| Type "M" Mortar | KDOT Type C Certification | CI
| Steel Plates with Detectable Warning Surface | KDOT Type C Certification | CI
| Detectable Warning Pavers | KDOT Type B Certification | CI
Curb 4K Concrete (All Types)
| KCMMB Miles (Supplier) Mixes 860022,860024 | Mix Design | CI
| KCMMB Miles (Supplier) All Mixes | Mix Design | CI
| KCMMB WCI (Supplier) All Mixes | Mix Design | CI
| Liquid Membrane-Forming Compounds (Curing Compound) | KDOT Type C Certification | CI
| Urethane Sealant | IAW of the Specifications | CI
| Expansion Material | KDOT Type D Certification | CI
| Reinforcing Steel Grade (40) | KDOT Type B Certification | CI
PCCP
| KCMMB | Mix Design | CI
| Dowel Bars and Baskets | KDOT Type B Certification | CI
| Expoxy Coated Tie Bars | KDOT Type B Certification | CI
| Tie Bar Supports | KDOT Type B Certification | CI
| Liquid Membrane-Forming Compounds | KDOT Type C Certification | CI
| Curing Compound (Resin) | KDOT Type C Certification | CI
| Hot Pour Joint Sealant | KDOT Type C Certification | CI
| Expansion Material | KDOT Type C Certification | CI
Paver Brick
| KCMMB Miles (Supplier) All Mixes | Mix Design | CI
| KCMMB Miles (Supplier) Mixes 860022,860024 | Mix Design | CI
| Paver Brick | KDOT Type B Certification | CI
| Geotextile Fabric (Geotex 801) | KDOT Type D Certification | CI
RCB Cast-In-Place (4K / 5K) (ALL)
| KCMMB WCI (Supplier) All Mixes | Mix Design | CI
| KCMMB Seal Course WCI ((Supplier)) All Mixes | Mix Design | CI
| Waterplug | KDOT Type D Certification | CI
| Reinforcing Steel Grade (60) | KDOT Type B Certification | CI
| Neoprene Rubber Seal | KDOT Type C Certification | CI
| Angle Iron for Neoprene Rubber Seal | KDOT Type C Certification | CI
| High Chair | IAW of the Specifications | CI
| Liquid Membrane-Forming Compounds (Curing Compound) | KDOT Type C Certification | CI
| Type "B" Expansion Material | KDOT Type D Certification | CI
| Bentonite | KDOT Type C Certification | CI
| Foundation Stabilization | KDOT Type B Certification | CI
| Granular Wingwall Backfill | KDOT Type B Certification | CI
| Geotextile Fabric (for underdrains) (Geotex 801) | KDOT Type D Certification | CI
Steel Handrail for RCB (ALL)
| Handrail | Shop Drawings | CO
| Epoxy Adhesive for Bolts | KDOT Type C Certification | CO
| Anchor Bolts for Structural Uses | KDOT Type B Certification | CO
Pre-Cast RCB (4K / 5K) (ALL)
| Lifting Device | Details | CO
| Precast Structure Segments | Laying Schedule | CO
| Design Calculations - BOXCAR Output | Calculations | CO
| Precast RFB Design | Drawing | CO
| External Sealing Bands | KDOT Type D Certification | CO
| 28 Day Concrete Compressive Strength | Test Results | PM
| Bentonite | KDOT Type C Certification | CI
Retaining Walls (4K / 5K)
| KCMMB WCI (Supplier) All Mixes | Mix Design | CI
| Form Liner | KDOT Type C Certification | CI
| Reinforcing Steel Grade (60) | KDOT Type B Certification | CI
| Reinforcing Steel Grade (60) Tract 99 | KDOT Type B Certification | CI
| Reinforcing Steel Grade (60) Tract 61 | KDOT Type B Certification | CI
| Type "B" Expansion Material | KDOT Type D Certification | CI
| Granular Backfill 57 Rock | KDOT Type B Certification | CO
| PVC Water Stop (9") | KDOT Type D Certification | CI
| Geotextile Fabric (for underdrains) (Geotex 801) | KDOT Type D Certification | CI
| 6" Type "H" Pipe Underdrain | KDOT Type D Certification | CI
| Wall Form Liner Treatment System | IAW of the Specifications | CI
Steel Handrail for Retaining Walls
| Handrail | Supplier | CO
| Wall (State if Multiple walls for Project) | Shop Drawings | CO
| Epoxy Adhesive for Bolts | KDOT Type C Certification | CO
| Anchor Bolts for Structural Uses | KDOT Type B Certification | CO
Integral Sidewalk and Retaining Walls (4K)
| KCMMB WCI (Supplier) All Mixes | Mix Design | CI
| Form Liner | KDOT Type C Certification | CI
| Reinforcing Steel Grade (60) | KDOT Type B Certification | CI
| Liquid Membrane-Forming Compounds (Curing Compound) WCI | KDOT Type C Certification | CI
| Type "B" Expansion Material | KDOT Type D Certification | CI
| Granular Backfill 57 Rock | KDOT Type B Certification | CI
| PVC Water Stop | KDOT Type D Certification | CI
| Geotextile Fabric (for underdrains) (Geotex 801) | KDOT Type D Certification | CI
| 6" Type "H" Pipe Underdrain | KDOT Type D Certification | CI
| 6" Type "H" Pipe Underdrain (2nd Submittal) | KDOT Type D Certification | CI
| Wall Form Liner Treatment System | IAW of the Specifications | CI
Modular Retaining Wall
| Block | KDOT Type B Certification | CI
| KCMMB 4K (Supplier) | Mix Design | CI
| Granular Backfill 57 Rock | KDOT Type B Certification | CI
| Geotextile Fabric (for underdrains) (Geotex 801) | KDOT Type D Certification | CI
| Adhesive | KDOT Type C Certification | CI
| Shop Drawing / Engineering | Shop Drawing / Engineering | CO/PM
Storm Sewer
| Precast Structures Cre-Tex KCMMB CCP LAW 5K WCFA (Q) | Mix Design | CI
| Precast Structures | Shop Drawings & Mix Design | CO
| HDPE Storm Sewer Pipe and Accessories | KDOT Type B Certification | CI
| Manhole Steps | KDOT Type D Certification | CI
| Post Construction Video | IAW of the Specifications | PM
| Heavy Duty Ring and Lid | KDOT Type B Certification | CI
| Medium Duty Ring and Lid | KDOT Type B Certification | CI
| Single Grate Inlet Ring and Lid | KDOT Type B Certification | CI
| Reinforced Concrete Pipe | KDOT Type D Certification | CI
| Inlet Steel Frame Supplier | KDOT Type B Certification | CI
| Kincaid Flowable Fill RF144C | Mix Design | PM
| KCMMB 4K (Collars, Inverts, Pipe Collars) (Supplier) | Mix Design | CI
| Stormwater Quality Units (SQU) | Shop Drawings | CO
Reinforcing Steel
| Grade 40 (Standard) | KDOT Type B Certification | CI
| Grade 60 (Standard) | KDOT Type B Certification | CI
Expansion Material
| Fiber Expansion Joint-Curb | KDOT Type D Certification | CI
| Fiber Expansion Joint-Sidewalk | KDOT Type D Certification | CI
| Urethane Sealant | IAW of the Specifications | CI
Underdrain
| Underdrain (Type H) | KDOT Type D Certification | CI
| Underdrain (Type L) | KDOT Type D Certification | CI
| Underdrain Outlet Pipe (Type K) | KDOT Type D Certification | CI
| Underdrain Outlet Pipe (Type E) | KDOT Type D Certification | CI
| Geotextile Fabric (for underdrains) (Geotex 801) | KDOT Type D Certification | CI
| Geotextile Fabric (For OP Special) | KDOT Type D Certification | CI
| Aggregate (UD-1) | KDOT Type B Certification | CI
Fly Ash and Provider
| Fly Ash | KDOT Type B Certification | CI
| Supplier(s) Jeffrey |  | CI
Sanitary Sewer
| Manhole 4' and 5' Diameter | Shop Drawings | CO
| Manhole Steps | KDOT Type D Certification | CO
| Manhole Rings and Lids | KDOT Type D Certification | CI
| 6"PVC Pipe (SDR-17) Changed to SDR 26 By JCWW | KDOT Type D Certification | CO
| 8" PVC Pipe (SDR-35) Changed to SDR 26 By JCWW | KDOT Type D Certification | CO
| 15" Sanitary Sewer DIP Protecto 401 Deleted By JCWW | KDOT Type D Certification | CI
| 15" PVC SDR 26 Sanitary Sewer Added by JCWW | KDOT Type D Certification | CO
| Encasement KCMMB (4K) (Supplier) All KCMMB Mixes | Mix Design | CI
| 30" Steel Encasement | IAW JCCW | CI
| Calibration of Testing Equipment | IAW JCCW | CI
Restoration
| Fescue Sod (Site Visit by the PI) | KDOT Type B Certification | CI
| Fescue Sod Fertilizer | KDOT Type B Certification | CI
| Fescue Seed Mix | KDOT Type B Certification | CI
| Fescue Seed Mix Fertilizer | KDOT Type B Certification | CI
| Bluegrass Sod (Site Visit by the PI) | KDOT Type B Certification | CI
| Bluegrass Sod Fertilizer | KDOT Type B Certification | CI
| Bluegrass Seed Mix | KDOT Type B Certification | CI
| Bluegrass Seed Mix Fertilizer | KDOT Type B Certification | CI
| Temporary Seed Mix | KDOT Type B Certification | CI
| Temporary Seed Fertilizer | KDOT Type B Certification | CI
| Tree Replacement Nursey Supplier | Nursery Source | CI
| Landscape Nursey Supplier | Nursery Source | CI
Erosion Control
| Erosion Control Mat (Type A) | KDOT Type D Certification | CI
| Straw Wattle | KDOT Type D Certification | CI
| Biodegradable Log(s) | KDOT Type D Certification | CI
| Area Inlet Protection | IAW Project Plans | CI
| Curb Inlet Protection | IAW Project Plans | CI
| Junction Box Protection | IAW Project Plans | CI
| Construction Entrance (2" to 3" Rock) | IAW Project Plans | CI
| Construction Entrance (Geotextile Non-Woven) | IAW Project Plans | CI
| Temporary Ditch Check, Type I (3" to 6" Rock) | IAW Project Plans | CI
| Temporary Ditch Check, Type II (12" Rip Rap and 3" to 6" Rock) | IAW Project Plans | CI
| Silt Fence | KDOT Type D Certification | CI
| Hydraulic Mulch | KDOT Type D Certification | CI
Service Water Line
| Material (s) | KDOT Type B Certification | CI
Fencing
| Chain Link Fence (Temporary) | KDOT Type D Certification | CI
Sprinkler System
| Lawn Sprinkler System | Catalog Cuts | CO
Land Corner Monument Box
| Monument Box | KDOT Type D Certification | CI
Rip Rap
| Rip Rap 18" Light | KDOT Type B Certification | CI
| Rip Rap 24" Light | KDOT Type B Certification | CI
| Rip Rap 24" 1/2 Ton Heavy | KDOT Type B Certification | CI
| KDOT 1/4 Ton | KDOT Type B Certification | CI
| KDOT 1/2 Ton | KDOT Type B Certification | CI
| D-50 (6") | KDOT Type B Certification | CI
| Geotextile Fabric (For OP Special) | KDOT Type D Certification | CI
Street Lighting
Cable
| Locating Cable (Red) 1c No. 10 AWG THHN/THWN | Approved Materials List | TS
| Electrical Service Power Cable 3-1c #2 AWG | Approved Materials List | TS
| Distribution Cable 3-1c No. 4 AWG Type USE | Approved Materials List | TS
| Pole & Bracket Cable 1c No. 10 AWG Type THHN/THWN | Approved Materials List | TS
Break-away Pole Device
| Frangible Bases or Couplings | Approved Materials List | TS
Concrete Mix Design
| Controller Foundation | Mix Design | TS
Conduit and Fittings
| Schedule 40 PVC Conduit, 1" (for Ground Cable Equipment) | Approved Materials List | TS
| Sch 40 PVC (Gray) Conduit 3" or SDR 13.5 HDPE (Blk w/Red Stripe) Conduit 2" | Approved Materials List | TS
| Sch 80 PVC (Grray) Conduit 3" | Approved Materials List | TS
| PVC Conduit Couplings | Approved Materials List | TS
| Standard PVC Conduit Elbows | Approved Materials List | TS
| Large Radius PVC Conduit Elbows (Electrical Service) | Approved Materials List | TS
| SDR 13.5 HDPE (Gray) Conduit, 2" | Approved Materials List | TS
| SDR 13.5 HDPE (Gray) Conduit, 3" | Approved Materials List | TS
| HDPE Conduit Couplings | Approved Materials List | TS
Control Centers
| Aluminum Control Center | Approved Materials List | TS
Electrical Connector Kits & Fuses
| Break-Away Non-Fussed Connector Kits | Approved Materials List | TS
| Break-Away Fused Connector Kits | Approved Materials List | TS
| 8 AMP Fuse | Approved Materials List | TS
| Multiple Streetlight Tap Connector | Approved Materials List | TS
| Splice Kit | Approved Materials List | TS
Grounding Equipment
| 5/8" x 10' Ground Rod | Approved Materials List | TS
| Ground Rod Clamp (5/8") | Approved Materials List | TS
| Solid Copper Ground Cable (Bare Copper # 6 AWG) | Approved Materials List | TS
Junction Boxes &Service Boxes
| Type 1 Service Box | Approved Materials List | TS
| Type 1 Junction Box | Approved Materials List | TS
| Type 2 Junction Box | Approved Materials List | TS
Lamps
| Class E LED Lamp | Approved Materials List | TS
| _____ Watt High Pressure Sodium (HPS) Lamp | Approved Materials List | TS
Luminaires
| Cobra-Head Luminaire | Approved Materials List | TS
| Post-Top Luminaire | Approved Materials List | TS
| LED Class ___ Luminaire | Approved Materials List | TS
| LED Class ___ Luminaire | Approved Materials List | TS
| LED Class ___ Luminaire | Approved Materials List | TS
Poles
| 40' Aluminum Pole (OP401) | Approved Materials List | TS
| 40' Aluminum Pole (OP402) | Approved Materials List | TS
| 40' Aluminum Pole (OP403) | Approved Materials List | TS
| 30' Aluminum Pole (OP301) | Approved Materials List | TS
| 30' Aluminum Pole (OP302) | Approved Materials List | TS
| 30' Aluminum Pole (OP303) | Approved Materials List | TS
| 14' Aluminum Pole (OP14) | Approved Materials List | TS
| Truss Member Bracket Arms - ____' | Approved Materials List | TS
| Single Member Bracket Arms - ____' | Approved Materials List | TS
Pole Foundations
| Type F1 Screw-in Foundations | Approved Materials List | TS
| Type F2 Screw-in Foundations | Approved Materials List | TS
| Type T1 Screw-in Foundations | Approved Materials List | TS
| Type R Screw-in Foundations | Approved Materials List | TS
| Concrete Foundation for Pole | Approved Materials List | TS
| Concrete Pole Foundation Cap | Approved Materials List | TS
Photocell
| Photocell | Approved Materials List | TS
Traffic Signals
Anchor Bolts
| Anchor Bolts for Mast Arm Poles | Shop Drawings | TS
| Anchor Bolts for Pedestrian Poles | Shop Drawings | TS
| Pedestrian Push Button Pole Anchors and Epoxy | Approved Materials List | TS
Backplates
| Backplate 5" (3 Section Vehicular Signal) | Approved Materials List | TS
| Backplate 5" (4 Section Vehicular Signal) | Approved Materials List | TS
Cable
| Multi-Conductor Cable 7c # 14 AWG | Approved Materials List | TS
| Multi-Conductor Cable 2c # 14 AWG (From Ped Pushbutton to Pole Base) | Approved Materials List | TS
| Video Detection Cable | Approved Materials List | TS
| CCTV Camera Data Cable | Approved Materials List | TS
| Electrical Service Power Cable 3-1c #4 AWG | Approved Materials List | TS
| Ethernet Cables (6' long) | Approved Materials List | TS
| Detector Loop Wire 1c #14 AWG THHN/THWN in PVC Tube | Approved Materials List | TS
| Shielded Detector Lead-In 2c # 14 AWG | Approved Materials List | TS
| CNG Monitoring Cable 3c # 14 AWG | Approved Materials List | TS
| CNG Power Cable 3c # 2 AWG | Approved Materials List | TS
| CNG Alarm Cable 2c # 14 AWG | Approved Materials List | TS
| Emergency Vehicle Pre-empt (EVP) Cable | Approved Materials List | TS
| Radar Detector Home Run Cable | Approved Materials List | TS
| Radar Detector Cable Harness | Approved Materials List | TS
| Illuminated Street Name Sign Cable 3c # 14 AWG | Approved Materials List | TS
| Illuminated Blank-Out Sign Power Cable (3c # 14 AWG) | Approved Materials List | TS
| Stranded Copper Ground Cable (Green) 1c#10 AWG THHN/THWN | Approved Materials List | TS
| Stranded Copper Locating Cable (Red) 1c#10 AWG THHN/THWN | Approved Materials List | TS
Concrete Mix Design
| Controller Foundation & Pole Foundations | Mix Design | TS
Conduit and Fittings
| Sch 40 PVC (Gray) Conduit 2" or SDR 13.5 HDPE (Blk w/Red Stripe) Conduit 2" | Approved Materials List | TS
| Sch 40 PVC (Grray) Conduit 2" | Approved Materials List | TS
| PVC Conduit Couplings | Approved Materials List | TS
| Standard PVC Conduit Elbows | Approved Materials List | TS
| Large Radius PVC Conduit Elbows (Electrical Service) | Approved Materials List | TS
| SDR 13.5 HDPE (Black w/White Stripe) Fiber Optic Conduit 1.5" | Approved Materials List | TS
| SDR 13.5 HDPE (Black w/White Stripe) Fiber Optic Conduit 2" | Approved Materials List | TS
| SDR 13.5 HDPE (Black w/White Stripe) Fiber Optic Conduit 3" | Approved Materials List | TS
| SDR 13.5 HDPE (Black w/White Stripe) Fiber Optic Conduit 4" | Approved Materials List | TS
| HDPE Conduit Couplings | Approved Materials List | TS
Controller Cabinet
| 333 Hybrid Cabinet w/ 8" Base Riser | Approved Materials List | TS
| 332 Stretch Hybrid Cabinet w/ 8" Base Riser | Approved Materials List | TS
| 333 Double Wide Cabinet w/ 8" Base Riser | Approved Materials List | TS
| 332 Single Cabinet w/ 8" Base Riser | Approved Materials List | TS
| ATC Cabinet w/ 8" Base Riser | Approved Materials List | TS
Controller & Equipment
| Rackmount Controller Unit w/ Firmware | Approved Materials List | TS
| Malfunction Management Unit (MMU) | Approved Materials List | TS
| Conflict Monitor | Approved Materials List | TS
| Cabinet Surge Protector Unit | Approved Materials List | TS
| Electrical Service Surge Protector Unit | Approved Materials List | TS
| 242 DC Isolator | Approved Materials List | TS
| 204 Flasher Unit | Approved Materials List | TS
| 200 Switchpack (Load Switch) | Approved Materials List | TS
| 430 Flasher Transfer Relay | Approved Materials List | TS
| Two Channel Detector | Approved Materials List | TS
| Four Channel Detector | Approved Materials List | TS
| Bus Interface Unit (BIU) | Approved Materials List | TS
| EVP Discriminator Module 2-Channel | Approved Materials List | TS
| EVP Discriminator Module 4-Channel | Approved Materials List | TS
| K1 Control Relay | Approved Materials List | TS
| Power Distribution Unit (Rack Mounted) 8 Recept. | Approved Materials List | TS
| RJ-45 Data Protector for CCTV Cameras | Approved Materials List | TS
| Radar SDLC Cabinet Interface Module | Approved Materials List | TS
Detectors
| Emergency Vehicle Pre-empt (EVP) Detector | Approved Materials List | TS
| Standard Pedestrian Pushbutton | Approved Materials List | TS
| Audible Pedestrian Signal System | Approved Materials List | TS
| Video Detection System ( - Camera) | Approved Materials List | TS
| CCTV Camera w/ RJ-45 Connector Kit & High PoE Midspan 1-port | Approved Materials List | TS
| Advanced Radar Detector Sensor | Approved Materials List | TS
| Presence Radar Detector Sensor | Approved Materials List | TS
Electrical Service Pedestal Enclosures
| Secondary Aluminum Service Enclosure w/30amp Main | Approved Materials List | TS
Grounding Equipment
| Ground Rod (5/8" x 8') Service Boxes | Approved Materials List | TS
| Ground Rod & Clamp (5/8" x 10') | Approved Materials List | TS
| Ground Rod Clamp (5/8") | Approved Materials List | TS
| Solid Bare Copper Ground Wire 1c # 6 AWG | Approved Materials List | TS
Junction Boxes & Service Boxes
| Junction Box Type 1 | Approved Materials List | TS
| Junction Box Type 2 | Approved Materials List | TS
| Service Box Type 1 | Approved Materials List | TS
| Service Box Type 2 | Approved Materials List | TS
Mounting Brackets for Signal Equipment
| Mast Arm Vehicle Signal Head Bracket (3 & 4 Section) | Approved Materials List | TS
| Side Pole Bracket (Vehicle & Pedestrian Signal Heads) | Approved Materials List | TS
| Mini Astro Brac for Emergency Vehicle Pre-emption (EVP) Detector | Approved Materials List | TS
| CCTV Camera Mounting Arm Bracket | Approved Materials List | TS
| Video Detection Camera Mounting Bracket (Luminaire Arm) | Approved Materials List | TS
| Combined Video Detection Camera /Signal Head Mounting Bracket (Mast Arm) | Approved Materials List | TS
| Video Detection Camera Mounting Bracket (Side of Pole) | Approved Materials List | TS
| Radar Detector Mounting Bracket | Approved Materials List | TS
Poles, Mast Arms and Luminaire Arms
| Galvanized Steel Signal Pole, Mast Arm & Luminaire Arm | Shop Drawings | TS
| Traffic Signal Pedestal Pole Aluminum (14') | Approved Materials List | TS
| Traffic Signal Pedestal Pole Aluminum (13') | Approved Materials List | TS
| Traffic Signal Pedestal Pole Aluminum (9') | Approved Materials List | TS
| Cast Aluminum Pedestrian Pole Base | Approved Materials List | TS
| Cast Aluminum Pedestrian Pole Cap | Approved Materials List | TS
| Pedestal Pole Mounting Collar | Approved Materials List | TS
| Pedestrian Push Button Pole | Approved Materials List | TS
Power Backup System
| Compressed Natural Gas (CNG) Generator & Cabinet w/Landscaping | Approved Materials List | TS
| Concrete Conpressed Natural Gas (CNG) Generator Pad | Approved Materials List | TS
| Battery Backup UPS System & Accessories | Approved Materials List | TS
| UPS Batteries and Cables | Approved Materials List | TS
| Portable Generator Outlet with 8' Cable Harness | Approved Materials List | TS
Signal Heads
| Vehicular Signal Head | Approved Materials List | TS
| Pedestrian Signal Head (1 Section) | Approved Materials List | TS
| Red Ball LED Kit | Approved Materials List | TS
| Yellow Ball LED Kit | Approved Materials List | TS
| Green Ball LED Kit | Approved Materials List | TS
| Red Arrow LED Kit | Approved Materials List | TS
| Yellow Arrow LED Kit | Approved Materials List | TS
| Green Arrow LED Kit | Approved Materials List | TS
| Dual Indication Green/Yellow LED Arrow Kit | Approved Materials List | TS
| Orange/White "Hand/Man" Countdown LED Kit | Approved Materials List | TS
Sign Brackets
| Illuminated Street Name Sign Mast Arm Bracket | Approved Materials List | TS
| Overhead Street Name Mast Arm Sign Bracket | Approved Materials List | TS
| Mast Arm Sign Bracket | Approved Materials List | TS
| Side of Pole Sign Bracket | Approved Materials List | TS
| Side of Pole Sign Banding | Approved Materials List | TS
| Side of Pole Sign Buckle | Approved Materials List | TS
Traffic Signal Signs
| Illuminated Street Name Signs (19" x - ") | Shop Drawings | TS
| Illuminated Street Name Signs (19" x - ") | Shop Drawings | TS
| D3-1 Overhead Street Name Signs | Shop Drawings | TS
| Aluminum Sign Blanks & Type XI Sheeting | Approved Materials List | TS
Fiber Optic
Cable
| Fiber Optic Cable | Approved Materials List | TS
| Fiber Optic Patch Cable | Approved Materials List | TS
| ITS Termination Drop Cable | Approved Materials List | TS
Conduit and Fittings
| SDR 13.5 HDPE Fiber Conduit | Approved Materials List | TS
| HDPE Couplings | Approved Materials List | TS
Ethernet Switch Equipment
| Fiber Optic Ethernet Switch and Power Supply | Approved Materials List | TS
| Extension Module | Approved Materials List | TS
| Switch Rack | Approved Materials List | TS
| SFP Modules | Approved Materials List | TS
Locating Equipment
| 1c #10 AWG Tracer Cable | Approved Materials List | TS
| 5/8" x 8' Ground Rod | Approved Materials List | TS
| Ground Rod Clamp (5/8") | Approved Materials List | TS
Service Boxes
| Type 1 Fiber Optic Service Box | Approved Materials List | TS
| Type 2 Fiber Optic Service Box | Approved Materials List | TS
Splice Enclosures
| Fiber Optic Splice Enclosures | Approved Materials List | TS
Pavement Marking
Durable Patterned Cold Plastic
| Yellow Durable Patterned Cold Plastic | Certification | TS
| White Durable Patterned Cold Plastic | Certification | TS
Integrated Multi-Polymer
| Yellow Integrated Multi-Polymer | Certification | TS
| White Integrated Multi-Polymer | Certification | TS
Glass Beads
| Glass Beads | Certification | TS
Paint
| Yellow Paint | Certification | TS
| White Paint | Certification | TS
Preformed Thermoplastic Tape
| Yellow Performed Thermoplastic Markings | Certification | TS
| White Performed Thermoplastic Markings | Certification | TS
Thermoplastic
| Yellow Thermoplastic Pavement Markings | Certification | TS
| White Thermoplastic Pavement Markings | Certification | TS
Urethane Acrylate
| Yellow Urethane Acrylate Pavement Markings | Certification | TS
| White Urethane Acrylate Pavement Markings | Certification | TS
Permanent Signing
Aluminum Sign Blanks
| Overhead Street Name Signs | Catalog Cuts | TS
| Ground Mounted Street Name Signs | Catalog Cuts | TS
| Aluminum Sign Blanks | Certification | TS
Sign Brackets
| Mast Arm Sign Mounting Astro Bracket | Approved Materials List | TS
| Street Name Sign Side Mounting Bracket | Approved Materials List | TS
| Round Pole Mounting Sign Brackets | Approved Materials List | TS
| Steel Sign Banding and Buckles | Approved Materials List | TS
Posts
| Sign Posts 1 3/4" x 1 3/4" x Var. | Approved Materials List | TS
| Post Anchor 2" x 2" x 3' | Approved Materials List | TS
| Anchor Sleeves 2 1/4" x 2 1/4" x 18" | Approved Materials List | TS
| Breakaway Concrete Surface Mount Anchor | Approved Materials List | TS
| Breakaway Concrete Paver Anchor and Sleeve | Approved Materials List | TS
Sign Sheeting
| Electronic Cuttable Film | Approved Materials List | TS
| Retro-reflective Sheeting, Type XI | Approved Materials List | TS
Traffic Conntrol
Arrow Panels
| Flashing Arrow Panels | Approved Materials List | TS
Barricades
| Type I Barricades | Approved Materials List | TS
| Type II Barricades | Approved Materials List | TS
| Type III Barricades | Approved Materials List | TS
| ADA Pedestrian Barricades | Approved Materials List | TS
Tubular Delineators
| Tubular Delineators | Approved Materials List | TS
Changeable Message Signs
| Changeable Message Signs | Approved Materials List | TS
Channelizing Devices
| Conical Delineators | Approved Materials List | TS
| Drums | Approved Materials List | TS
Inertial Barrier Systems
| Sand Barrels | Shop Drawings | TS
Sign Sheeting
| Sign Sheeting | Approved Materials List | TS
Sign Stands
| Sign Stands | Approved Materials List | TS
Temporary Pavement Marking
| Paint | Approved Materials List | TS
| Removable Tape | Approved Materials List | TS
| Non-Removable Tape | Approved Materials List | TS
Warning Lights
| Type A Flashers | Approved Materials List | TS
PM = Project Manager
CI = Construction Inspector
CO = Consultant
TS = Traffic Services
CF = City Forester